## Sheet2
PCT | Comments | DES 2 payment 2006/07 | Incentive scheme agreed with consortia | description of scheme | Date incentive scheme signed off /forecast date for sign off | Information provision agreed with consortia | Governance framework agreed | Budget agreed with consortia/practice | Date budget signed off/forecast date for sign off | description of budget setting | PBC plans signed off
Luton |  | Calculations being finalised and discussed with PbC groups - will be completed by 15/06/07 | Budgets and incentive scheme fully agreed with PbC groups and circulated to all practices. | The incentive scheme covers 5 parameters - 1st O'p, F/U, Elec, Non Elec & Prescribing spend. The scheme starts at a level before the savings increment was taken off to arrive at the budget for each category and rewards/penalises the PbC group increasingly with each savings increment below/above the starting point. The net reward paid is the aggregate of the 5 elements. | Done | MIDAS software available on GP desktops, public health support and data analyst in post; monthly performance reports against the incentive scheme. | Framework document is going to the PCT board on June 12th | Done (methodology) | end of May | Acute budgets based upon '06/'07 outturn plus known events (eg 18 weeks) less savings plan levele for each category split on a 50/50 DH Fair Share/Historic basis. Prescribing based upon '06/'07 outturn plus national uplift less savings plan, split on an 80/20 Astro/PU basis. | July
Herts | Budget sign off outstanding | With latest SUS data available, some practices may not receive their DES 2 payments as the targets may not be reached. The PCT has agreed that payments are dependent on outputs. | Yes. New PBC LES for 2007/08 agreed for investment in practices and localities to achieve level PBC commitment. Approx resources available £3.1million (£2.75 per patient) | Les has several tiers including 1.) GP agreeing to commissioning process and duties there in 2) for collation of data and clinical validation reporting 3) reward dependant on freed up resources All rewards have levels of achievement | signed off end of March agreed with Practices | Difficulty in accessing robust information to disseminate to practice level across PCT - issue raised and is being managed at Executive level. SUS process and deadlines result inherent delays and reconciliation issues which creates a 3 month time-lag of validated activity. | Governance Framework agreed with both PEC and Board. PEC representation on PBC Governance Committee. Any change to clinical services approved at Governance Committee. | 1st draft of PBC budgets issued for discussion. PCT budgets revised May07 and therefore PBC budgets will need to be revised to be aligned with PCT budgets and to reflect agreed scope. Scope of budget needs to be agreed across 11 localities. | Estimate 20th June for reissue of revised budgets. 30th June 2007 for sign off with practices | Budgets for acute secondary PBR activity and prescribing set in line with DH guidance. Guidance focussed on acute which is only approx 50% of total budget. Much of remainder issued on capitation basis. | 8 (out of 11) plans signed off. Remainder to be submitted to next PBC Governance Committee
Bedfordshire |  | not as yet paid as need info to determine payments | yes | Payments based on effective demand management paid at the end of the financial year. Split into payment to refect achievement and effort - | 2007-06-01 | Dr Foster at practice level - and monthly reports from PCT to practices consortia validate information | Governance structure in place since Jan - includes strategic commissioning board to sign off plans and business cases - after PEC review - | yes | 2007-05-31 | Budgets set through reconciliation of capactiy plan with historic outurn ( compared to fairshare) | None received yet
PCT | Comments | DES 2 payment 2006/07 | Incentive scheme agreed with consortia | description of scheme | Date incentive scheme signed off /forecast date for sign off | Information provision agreed with consortia | Governance framework agreed | Budget agreed with consortia/practice | Date budget signed off/forecast date for sign off | description of budget setting | PBC plans signed off
South West Essex |  | some have been agreed others are under negotiation | Yes | Three components Component 1- Engagement (remunerating for Microvalidation, attendance at PBC Cluster meetings and undertaking audits Component 2- Health Improvement (extension of QOF for PCTs key target clinical domains + prescribing) Component 3- Demand Management (rewarding practices for delivering activity levels inline with capacity plan) | SMT 4th June | Sollis system in place at practice level will support PBC with data analysts also as well as data validation processes and clearnet data | Yes - 3 locality groups accountable to PCT financial & planning group ( clarity around PEC involvement) | Budget setting methodology agreed. Indicative budgets have been circulated- awaiting agreement from practices | Circulated 8th June 2007 | Historic spend for PBR, GMS/PMS and Prescribing. Fairshare for all other spends. Budgets circulated with distance from fair share target information. | Cluster plans being developed
SE Essex | Incentive scheme sign off outstanding | There are a number of plans that achieved results and levels of apporpriate DES2 funding is being negotiated | Agreed in principle. To be formally adopted at PBC Ratification Group | Upfront element for engagement,reciept of plans,public and patient involvement, attendance at training and strategic events 2nd element related to achievement of targetsincluding demand management, new to follow up ratio, A & E activity all of which will have positive impact on budgets - | 21 st June - practices to sign up in July | Essa information on monthly basis | PBC Ratification Group agreed with ToR to sign off plans and subsequent buisness cases up to a level of £50K- sub committee of PEC. Draft conflict of Policy developed. PCT currently working with PBC groups to reduce numbers and form federations with GP startegic leads | Yes (one exception - prescribing) | Budgets reconciled and Board agreed April 2007 (based on agreed framework with practices) | Looked at fair share model for indicative budgets and compared with historic use in accordance with PBC toolkit - ultimately leading us to fairshare being reached 2009/10 | Outline plans for all PBC Groups signed off 15 March 2007
West Essex | Budget sign off to be confirmed | not achieved | Yes | A LESof 95p/hd of populaiton will be paid for produciton of action plan that is an implementation plan of the 06/07 comissioning plan. An additional les is set up to reward effective demand managemnet payment based on % reducitonn in activity and freed up resource in relation to budget | early may | yes -have purchased Sollis - for practice level to link with validating SUS/clearnet information | yes - PEC acts as commissioning board to sign off plans 3 locality clusters commissioning boards that the consortia feed into | No | week end 9th June | formulated with respect to historical out turn and reconciled to 07/08 planned activity including growth etc (3% withheld by PCT as contingency to manage financial risk) | activity plansforecast to be signedd of by the end of June
NE Essex | Draft budgets shared with PBC Groups and working to end of May deadline (achieved - budgets sent out end of May) | Have paid the DES2 for Colchester practices; part of DES2 for Tendring being made in May; remainder of this DES (was in 3 parts) being paid in June | yes | 3 payments 1) upfront in SLA form for engagement and resources 2) based on achievement of targets 3) effective management of budget | yes - signed off by Board for Parts 1 and 2 May 2007. Part 3 agreed with PBC Clinical Leads June 2007 | yes -monthly ESSA summary report format agreed with practices to provide headline information, data validation process being agreed, KPIs for budget management developed/PID for implementation of SOLLIS for all practices developed | 2 consortia boards and a PCT committee - ToR for PCT PBC committee considered by PEC in June; revised governance proposals to July Board for sign off | Yes -practice PBC Budgets agreed end of May 2007 and proportion of LIS funding blocked back to PBC Groups to support costs of clinical engagement | end of May | budgets based on historic out turn and compared to fairshare with strategy to align budgets with agreement by practice | Joint PBC/PCT commissioning priorities agreed; PBC Group plans not yet received
Mid Essex | Budget methodology not signed off | Panel established to review PBC achievement mid June. Recommendations to go to June Commissioining Board | Agreed with PBC consortia to split incentive scheme to two components. Component 1 distributed to practices and signed SLAs being returned to PCT. Component 2 continues to be discussed to ensure maximum engagement of practices at both end of the spectrum. | 3 payments 1)upfront for submission of plans and agreement to engage & manage leadership etc, 2) for achieving budget at end of year, 3) for achieving underspend in grades (all as income | May 23rd | SOLIS in place at practice level -the PCT provides practices monthly with data for validation generated through clearnet/SUS. In the interim practices to continue receiving ESSA data monthly. | Yes, framework revised to establish PCT commissioning Board and separate Procurement panel for maximum probity. | Last stage of data input - Addenbrookes currently underway. Expectation final indicative budgets to be with practices week ending June 15th. | June 24 (Comm Board) | compared historical outturn to fair share and this years available budget – to be set by the 18th April. Consortia accepting principle of top slice to pay deficit.
PCT | Comments | DES 2 payment 2006/07 | Incentive scheme agreed with consortia | description of scheme | Date incentive scheme signed off /forecast date for sign off | Information provision agreed with consortia | Governance framework agreed | Budget agreed with consortia/practice | Date budget signed off/forecast date for sign off | description of budget setting | PBC plans signed off
Suffolk | Reviewing information provision | IPSCOM have received part 1 of DES 2. Forest Heath and Haverhill have received DES 2. The remainder have had the qualifying period extended to September 07. | Yes | 4 payments in all 1) to consortia for admin upon signing up to MOU 2) submission of plan 3) Progress payments 4) 5% of whole freed up resource as income to practice, paid out of 30% | 26th April 07 at PBC Committee | Mimimum standards in guidance met, pending benchmark data from public health. PBC Information and BIS User Group established, inaugural meeting 22nd June 2007. | Yes, subject to PEC redefining their role later in the year due to change in guidance. | Yes | 26th April 07 | reviewed with individual practices - close to fair share -(1%) step to farishare if within 10% | MOU's for 6/8 agreed. Awaiting full PBC Plans for 7/8. Meanwhile business cases progressing (see update )
Norfolk |  | Currently assessing last years plans - perceive that they will be paying most practices the DES 2 payments | Yes revised incentive scheme agreed | £2 per capita in total 1st 1/2 based on submission of commissioning plan and agreement to engage in PBC meetings etc. 2nd half related to acfievement of plan with specific targets agreed adn milestones set. prescribing incentive separate LES incase practices not engaged with PBC are signed up to mangement of prescribing budget | 07/08 incentive scheme was signed off by PCT on 22nd May | Agreed Dr Foster until September local enterprise system - at practice level for validation report (working with PBC groups to improve practice level information) | PBC committee feeds into PCT board (PEC also involved to sign off service redesign proposals still requires work on relationship with PBC group) - 4 locality groups | Budget due out for sharing with practices 05/06/07 | 2007-06-05 | indicative budget plus growth +18 weeks +other investment less risk assessed CIP savings= PBC budget. Central risk contingency held to cover difference between gross CIP and risk assessed CIP. LES schemes will involve formal sign up to specific major demand management
Cambridgeshire | Budget still to be signed off | Target end June 07, month 12 data permitting | yes | Payment for Achieving Change and Engagement (PACE). Based on 06/07 DES principles: 2 payments, 1st for delivery of data validation, objectives agreed relating to prior approval and demand management systems as well as implementation of a practice/consortia lead; 2nd payment for achievement of objectives | Scheme agreed by PEC; target practice sign off end June 07 | Systems in place and agreed - using QUEBEC (information tool & QUTE a tool for practices to see acute and primary care events side by side (+ Dr Foster PBC) | three Area Commissioning Forums; PEC sub group - 'Quality & Governance Committee' agreeing plans & business cases | Budgets issued to practices (end May) | End June 07 | Historical budget reconciled with capacity plan with 1% movement to fair share | End June 07
Peterborough | Final draft of incentive scheme being debated early June with aim to achieve full sign up for 4th July Board. To be discussed at Weekly locality Chairs meeting 12th June 07, followed by PEC and Board processes in line with 4th July timescale. | YES , final calculations being undertaken. Anticipate info available for allocations August 07 | Full consultation in June meetings approval planned at Board in July 07. | Local incentive scheme based around 2 parts, Effort based upon evidence from practice and Results based upon agreed measures as outlined within the LIS. Fundamentally it identifies areas that PBC can both directly control and influence. the 1st four objectives have 2 incentive components, 1 as a sliding scale to support sign up to the scheme and evidence of effort. 2. linked to specific plans, once approved, being pump primed to enable full realisation of the cost improvement. This is underpinned by a PCT commitment to support a clear project approach to approve plans that reflects a clear need, delivers a positive budget position and also supports the locality in achieving an improvement on budget from baseline (current contract)figure. the scheme also highlights 1 specific national DES for Choose and Book as it was recognised as a vital element to supporting objectives 1-4 re referrals to secondary care and improving health. the Prescribing plan and business continuity plans are core requirements for primary care as a provider. | Confirmed for 4th July - | Locality reports will provide locality level data for contract plans & trajectories for non-electives; OP's; F/us. Comparative data from 06/07 will provide localities & practices with variance to historic patterns. Detailed information will be provided at a locality and practice level on 19 conditions to steer localities with support from Locality Support Officer. Aligned with reports for monthly SUS data for objectives in scheme via Quebec and Senior Information Analyst financial reports will provide spells and impact on budget of referrals patterns. work is progressing with practices to ensure primary prevention is appropriately monitored and does not replicate QOF incentives. Monthly locality reports will be supplemented with a full suite of reports reflecting the indicative budgets and referral pathways commissioned provided quarterly. | Two locality groups- Commissioning issues identified within the first half, and nominated public reps linked in with wider working groups. Plans developed by providers/ working groups are received for support at locality and approved via PEC. Plans that result in consultation/ significant contract changes are approved by the Board. Inter- practice agreement developed and sign up nearing completion. | full format being presented June 07 | 4th July 07 | Comparing historic out-turn to capacity plan and then to fairshare. Indicative budgets to be spilt by locality and practice. Final agreement on areas to be directly managed by localities by end June 07. | 4th July 07
Yarmouth & Waveney | Budgets and incentive schemes not signed off - PCT has agreed in principle an accountability framework, SLA for service, LIS scheme, Business case template, business plan format, Business process for submitting business cases. All are congruent to PCT LDP and recovery Plan. The formal sign off will be at the first meeting of the PCT commissioning sub group of the Board on 11 June. | Paid where evidenced | Agreed in principle. To be formally adopted at Commissioning sub group. | LIS based on 06/07 DES (two payments) 1st has two parts a)up front for engagement, b) year end 2nd for achieving targets - as income from freed up resources | no - | SLA agreed with PBC for the provision of infomation to be managed by a joint Information Board. | Two consortia, a PBC commissioning sub committee accountable to the PCT board. Also new business case approval process adopted by the Board which includes a new clinical liaison group as an advisory body to PBC and PCT | Being finalised. Agreed in principle to be top-sliced with PCT deficit. | 2007-06-11 | Where possible are setting budgets at fairshare with top slice agreed for management of deficit modelling will also consider activity allocations | Next Commissioning sub group meeting