## Sheet1
Hertfordshire Health Economy Audiology Action Plan for Achieving 6 week diagnostic tests by March 2008 and 18 week RTT targets by Dec 2008
| Aim | Objective | Outcome | To be achieved by | By whom | Organisations involved | Cost Implications 2007-08 | Risk | Comments
1 | To set up Health Economy wide steering group to drive the implementation of achieving 18 weeks in Audiology by Dec 2008. | Identify key parties to be involved in steering group | Have a robust group in place to implement work needed to achieve 18 weeks by Dec 2008 | 2007-06-01 | KG | WHHT/ENHT/PCTs | 0 | Low
|  | Develop terms of reference for the group | Ensure group has clearly defined role and responsibility for achieving 18 weeks by Dec 2008 | 2007-06-01 | KG | WHHT/ENHT/PCTs | 0 | Low
|  | Develop work plan for the group | Ensure group has clearly defined role and responsibility for achieving 18 weeks by Dec 2008 | 2007-06-01 | KG | WHHT/ENHT/PCTs | 0 | Low
|  | Develop robust systems to monitor the progress against achieving 18 weeks in Audiology | Evidence that progress towards achieving 18 week target by Dec 2008 is being achieved | 2007-06-01 | JV/CJ/TS/JR | WHHT/ENHT/PCTs | 0 | Low | Using the wider definition for delivery as defined in 'improving access' document.
| Urgently clear backlog of patients to ensure that there are no further breaches of 13 week target. | Develop and implemenet and action plan to clear backlog of patients currently waiting for a 1st appointment. | All patients seen within 13 weeks of referral | 2007-06-01 | EB/RR/PS | WHHT/ENHT/PCTs | TBC | High | c2000 breaches reported to SHA for April 2007. An emergency action plan to be developed to ensure that this backlog is cleared with immediate effect.
2 | Review referral protocol for Audiology and ENT to ensure that referrals are made to the correct department in a timely manner | Look at feasibility of piloting the use of primary care triage for audiology and ENT referrals | High quality referrals are received ensuring that any delays in the pathway are fully minimised | 2007-06-01 | PBC Leads | WHHT/ENHT/PCTs | 0 | Medium | Will seek agreement to identify 1 PBC group to work on this with the aim to roll out across the Health Economy.
|  | Implement Audiology referral form used by WHHT across the whole of the health economy to improve the quality of referrals received from primary care | High quality referrals are received ensuring that any delays in the pathway are fully minimised | 2007-06-01 | EB/RR/PBC Leads | WHHT/ENHT/PCTs | 0 | Medium
|  | Update directory of services at ENHT to ensure accurate information is available to Referers. | All patients are referred appropriately | 2007-06-01 | SE | ENHT | 0 | Medium
|  | Update directory of services at WHHT to ensure accurate information is available to Referers. | All patients are referred appropriately | 2007-06-01 | EB | WHHT | 0 | Medium
|  | Update Choose and Book systems to ensure accurate information is available to Referers | All patients are referred appropriately | 2007-06-01 | HW | WHHT/ENHT/PCTs | 0 | Low
3 | Review referral protocols for Trusts outside the catchments area to ensure referral is directed to appropriate Trust depending on type and level of service commissioned from these | Ensure GPs are aware that referrals for Hearing Aids should only be made to Acute Trust's where the PCTs fund this service (ENHT/WHHT/PAH) | All patients are referred appropriately | 2007-06-01 | PBC Leads | PCTs - lead to be agreed
|  | Monitor impact of referral criteria | All patients meet 6 week diagnostic target by March 2008 | 2007-06-01 | PBC Leads | PCTs | 0 | Medium
4 | Ensure that there is robust monitoring systems in place with each Trust that the PCTs commission audiology services from to ensure that no Hertfordshire patients breach the 6 week diagnostic target by March 2008 | Develop robust systems to monitor the progress against achieving 18 weeks in Audiology | All patients meet 6 week diagnostic target by March 2008 | 2007-06-01 | JV/CJ/TS/JR | PCTs
5 | Ensure that there is robust monitoring systems in place with each Trust that the PCTs commission audiology services from to ensure that no Hertfordshire patients breach the 18 week RTT target by December 2008 | Develop robust systems to monitor the progress against achieving 18 weeks in Audiology | All patients meet 18 week target by December 2008 | 2007-06-01 | JV/CJ/TS/JR | PCTs | 0 | High
4 | Ensure sufficient work up in primary care is taking place prior to referrals being made to secondary care | Develop criteria for work up to be done in primary care prior to referral being made to secondary care | All patients meet 6 week diagnostic target by March 2008 | 2007-07-01 | RR/EB/PS | WHHT/ENHT/PCTs
|  | Look at feasibility of developing primary care clinic for microsuction of earwax removal | Reduce number of inappropriate referrals received by audiology | 2007-07-01 | RR/JW/EB | ENHT/E&N PCT | TBC | Medium | May be possible to train DNs to provide this service at locations across the health economy
|  | Review outcome of Hearing Screening Programme for over 65's and decide whether this should be rolled out across the health economy | Reduce number of inappropriate referrals received by audiology | 2007-06-01 | RR | ENHT/E&N PCT | TBC | Low
5 | Develop robust criteria for the provision of digital hearing aids to ensure that resources are targeted at those who need them. | Advise GPs of referral criteria | Provide a robust local service to those Herts residents that meet the requirements for the service | 2007-07-01 | RR/EB/PS | WHHT/ENHT/PCTs | Potential cost saving | Low
|  | Ensure clinicians are aware of and following referral criteria | Provide a robust local service to those Herts residents that meet the requirements for the service | 2007-07-01 | SE/EB/PS/PBC Leads | WHHT/ENHT/PCTs | 0 | Low
|  | Monitor impact of referral criteria | Evidence that a robust local service to those Herts residents that meet the requirements is being provided | 2007-10-01 | PBC Leads | WHHT/ENHT/PCTs | 0 | Low
6 | Ensure Exceptional Treatment criteria for the provision of Bone Anchored Hearing Aids is fully implemented across all providers | Advise GPs of referral criteria | Provide a cost effective and timely service for Herts residents | 2007-09-01 | PBC Leads | PCTs | Potential cost saving | Low
|  | Ensure clinicians are aware of and following referral criteria | Provide a cost effective and timely service for Herts residents | 2007-09-01 | PBC Leads | PCTs | Potential cost saving | Low
|  | Monitor impact of referral criteria | Provide a cost effective and timely service for Herts residents | 2007-09-01 | PBC Leads | PCTs | Potential cost saving | Low
7 | Review current provision of BAHAs and look at feasibility of expanding the range of providers the service is commissioned from | Explore the possibility of ENHT providing a BAHA service locally to reduce impact on CUFHT | Provide a cost effective local service for E&N Herts residents | 2007-09-01 | KG/SE | ENHT/E&N PCT | Potential cost saving if ENHT can provide more cost effective service than CUHFT | Medium | ENHT are already providing BAHA service. Need to understand if they are being commissioned and funded to do this at present, whether they meet all relevant guidance to undertake this work and if the provision of this service is a cost effective alternative to that provided by CUFHT
8 | Ensure the provision of Cochlear implants is streamlined via Specialist Commissioning Team | Ensure that there is a clearly defined process for the provision of Cochlear Implants in place. | All patients are treated within agreed timescales | 2007-08-01 | CY | Specialist Commissioning | TBC | High
|  | Ensure that referrals for Cochlear Implants are made in a timely manner to the tertiary provider. | All patients are treated within agreed timescales | 2007-08-01 | CY | Specialist Commissioning | TBC | High
|  | Ensure RTT 18 weeks for Cochlear Implants as agreed by the DH is fully implemented | All patients are treated within agreed timescales | 2007-08-01 | CY | Specialist Commissioning | TBC | High
9 | Develop a robust process for reviewing all patients currently waiting for a reassessment | Ensure RTT is clear for all patients who request a self reassessment | All patients are treated within agreed timescales | 2007-08-01 | RR/EB | ENHT/WHHT/PCT |  | High
|  | Look at feasibility of GPs referring all patients requiring a reassessment in timeframes agreed with Acute providers | All patients are treated within agreed timescales | 2007-08-01 | RR/EB/PBC Leads | ENHT/WHHT/PCT |  | High
10 | Develop a one stop shop type service for patients that would be suitable to have OPA/Diagnostic and fitting in one session |  | Reduce unnecessary visits for patients and reduce waiting lists | 2007-09-01 | RR/EB | ENHT/WHHT | TBC | Medium
11 | Develop walk in clinics for patients for support and advise on hearing aids | Maintain existing service at ENHT | Reduce unnecessary OPAs for patients as support/batteries/advise etc can be given through this means | 2007-09-01 | RR/EB | ENHT/WHHT | TBC | Medium
|  | Look at feasibility of developing service at WHHT | Reduce unnecessary OPAs for patients as support/batteries/advise etc can be given through this means | 2007-09-01 | RR/EB | ENHT/WHHT | TBC | Medium
12 | Increase staffing capacity to reduce current waits for diagnostics | Increase staffing capacity at ENHT to reduce current wait of 12 weeks to 6 weeks by March 2008 | All patients meet 6 week diagnostic target by March 2008 | 2007-09-01 | RR | ENHT |  | High | Funding for Audiology at ENHT based on PbR through locally agreed tariff
|  | Increase staffing capacity at WHHT to reduce current wait of 13 weeks to 6 weeks by March 2008 | All patients meet 6 week diagnostic target by March 2008 | 2007-09-01 | EB | WHHT |  | High | Funding for Audiology at WHHT funded through block agreement so increase in funding will need to be made as part of SLA
|  | Fill audiology and admin vacancies as a matter of priority to reduce current wait of 6 months to 6 weeks by March 2008 | All patients meet 6 week diagnostic target by March 2008 | 2007-09-01 | PS | W Herts PCT | 0 | High | Posts frozen during 2006-07. Posts now unfrozen and team are in process of recruiting. Opportunities exist to fill vacant posts with staff undertaking additional hours or through locum cover.
13 | Extend the working day from 5pm to 8pm to create additional capacity to reduce current backlog in waiting times | Increase staffing capacity at ENHT to reduce current wait of 12 weeks to 6 weeks by March 2008 | All patients meet 6 week diagnostic target by March 2008 | 2007-09-01 | RR | ENHT | 200000 | High | Funding for Audiology at ENHT based on PbR through locally agreed tariff
|  | Increase staffing capacity at WHHT to reduce current wait of 12 weeks to 6 weeks by March 2008 | All patients meet 6 week diagnostic target by March 2008 | 2007-09-01 | EB | WHHT | 200000 | High | Funding for Audiology at WHHT funded through block agreement so increase in funding will need to be made as part of SLA
|  | Increase staffing capacity for paediatric service to reduce current wait of 6 months to 6 weeks by March 2008 | All patients meet 6 week diagnostic target by March 2008 | 2007-09-01 | PS | W Herts PCT | 0 | High | Vacant post for Audiologist. Monies from this post can be used to recruit locum to cover these hours until substantive appointment is made to this post.
14 | Explore the opportunities for increasing physical capacity for audiology services through providing outreach clinics in Primary Care | Look to provide physical space for WHHT service in Hemel | All patients meet 6 week diagnostic target by March 2008 | 2007-10-01 | EB | WHHT/W Herts PCT | 0 | High | There is a need to review the efficiency of audiology services.
|  | Look to provide physical space for ENHT service in Hitchin/Cheshunt | All patients meet 6 week diagnostic target by March 2008 | 2007-10-01 | RR | ENHT/E&N PCT | 0 | High
15 | Increase staffing capacity in order to ensure that 18 week diagnostic target is met by December 2008 | Increase staffing capacity at ENHT to reduce current backlog for reassessments and ensure that 18 week target is met | Al patients meet 18 week RTT target by December 2008 | 2007-10-01 | RR | ENHT | 100000 | High | Funding for Audiology at ENHT based on PbR through locally agreed tariff
|  | Increase staffing capacity at WHHT to reduce current backlog for reassessments and ensure that 18 week target is met | Al patients meet 18 week RTT target by December 2008 | 2007-10-01 | EB | WHHT | 106000 | High | Funding for Audiology at WHHT funded through block agreement so increase in funding will need to be made as part of SLA
|  | Increase staffing capacity for paediatric service to reduce current backlog for reassessments and ensure that 18 week target is met | Al patients meet 18 week RTT target by December 2008 | 2007-10-01 | PS | W Herts PCT | 45000 | High | Increase funding given to provider services. Includes admin support.
|  | Review the process for self referrals to audiology services with PBC groups | Ensure there are clear critieria for this group of patients and that PBC groups have ownership of referral process | 2007-07-01 | PBC Leads | PCTs | Potential cost saving | High | Need to decide whether self referrals to audiology should continue or whether all referrals should come via the GP.
16 | Discharge patients back to care of GP once treatment plan has been completed | Reduce number of patients that remain on follow-up lists | Reduce the number of unnecessary follow-up's required and free up space in clinics to see new patients | 2007-09-01 | RR/EB/PS | ENHT/WHHT/PCT | Potential cost saving | Medium
17 | Review skill mix within Audiology departments | Maximise staffing skills to ensure maximum benefits of existing resources are utikised to the full | Maximise outcomes from existing costs | 2007-09-01 | RR/EB/PS | ENHT/WHHT/PCT | 0 | Medium
18 | Look to continue to fund MHAS project that was funded through central monies in previous years | Ensure patients receive appropriate aids | Sufficient resources are available to meet demand | 2007-10-01 | RR/EB/PS | ENHT/WHHT/PCT | 200000 | Medium
19 | Review Domiciliary visits currently undertaken by ENHT | Ensure patients receive appropriate care in appropriate setting | Maximise resources | 2007-08-01 | RR | ENHT | Potential cost saving | Low
20 | Audit hearing loss pilot that has been undertaken at ENHT | Decide whether it is beneficial to implement pilot following audit | Maximise resources | 2007-08-01 | RR | ENHT | TBC | Low
| Total cost of achieving 18 week RTT for Audiology | [5 empty] | 851000
Key:
EB | Elaine Bond, Audiology Manager | WHHT
SE | Sharn Elton, General Manager | ENHT
KG | Kirsty Green, Planning Manager | Herts PCTs
CJ | Clare Jones, Contracts Manager | Herts PCTs
JR | Jane Rice, Head of Contracts | Herts PCTs
RR | Richard, Audiology Manager | ENHT
PBC | PBC Leads | Herts PCTs
PS | Pearl Selvaduri, Clinical Paed Audiology Lead | Herts PCTs
TS | Trudi Southam, S Contracts Manager | Herts PCTs
JV | Jan Vigor, Contracts Manager | Herts PCTs
CW | Carolyn Wilson, Business Manager | Herts PCTs
HW | Helen Whitty, C&B Lead | Herts PCTs
CY | Carolyn Young, Specialist Comm | Herts PCTs