## Sheet1
APPENDIX 1
| 2008-03-03 | 2008-03-10 | 2008-03-17 | 2008-03-24 | 2008-03-31 | 2008-04-07 | 2008-04-14 | 2008-04-21 | 2008-04-28 | 2008-05-05 | 2008-05-12
PBC shares and explores idea with colleagues within PCT. Agree key data requirements. | 2008-03-03: the earlier the better
Draft up outline Business Case and circulate for comments | bar: 2008-03-03 to 2008-03-17
Notify Governance Committee for agenda planning purposes | bar: 2008-03-03 to 2008-04-14
Business Group convened (may not be appropriate in all cases) | bar: 2008-03-24 to 2008-04-07
Finalise Business Case | 2008-04-14: by 16 April
Support Form signed off | 2008-04-14: by 16 April
Send Support form and finalised Business Case to Suzanne Novak/Nicky Poulain | 2008-04-14: by 16 April
Agenda finalised | 2008-04-21: 2008-04-23
Papers sent out | 2008-04-21: 2008-04-23
PBC Governance Committee | 2008-04-28: 2008-04-29
PBC Group receives confirmation of outcome | bar: 2008-05-05 to 2008-05-12