WELWYN HATFIELD COMMISSIONING PLAN 2008/09

National Priorities

| Objective/Priority | Action | Milestones | Lead | Timescale | Outcome |
| --- | --- | --- | --- | --- | --- |
| 18 week wait | The locality will contribute to ensure 90% of pathways for patients admitted to hospital, continuing to work within the appropriate referrals pathways | Delivery of 90% target breaching 17 weeks | Executive Board | Dec 2008 | 90% of pathways for patients admitted to hospital |
| Achieving financial health | Practices will continue to review received monthly costed activity information and spend against available budget. Practices will continue to demand manage their referrals; validate secondary care activity | Monthly reporting in place for robust financial performance management | Executive Board | March 2009 | Manage quality services within the available budget resources |
| patient experience | Work with PCT to improve patient surveys taking into consideration patients views and preferences on access; patient participation, local services | Produce performance monitoring arrangements with PCT; Good outcomes from the patient satisfaction surveys | Executive Board | Dec 2008 | Action taken on patients surveys & reported to boards quarterly |
| reductions in MRSA rates | Reduce elective care by utilising existing or establishing new services in primary care settings where appropriate | A locality interim audit of Cephalosporin & Quinalones prescribing | Locality | March 2011 | Reduction in anti-biotic prescribing |

Local Priorities

| Objective/Priority | Action | Milestones | Lead | Timescale | Outcome |
| --- | --- | --- | --- | --- | --- |
| Acute Services Review (ASR) The locality plans to be very involved in the design for the new Local General Hospital (LDGH) | We will build on initial work; involve local residents and other relevant bodies; review capacity/patient pathways in existing services; look at opportunities to redesign further services. | Transfer of care on 1st outpatient appointments (1460 reduction for our locality (from ASR) 50% reduction by December 2008 | Peter Shilliday/Locality | April 2009 | Interim plan developed to deliver modern first class services care for local residents that are appropriate for the early 21st century |
| Hertfordshire wide service models Redesign services and pathways of care, where appropriate moving the following services from acute to primary care in line with ASR and commission care closer to home. Diabetes Skin Health MSK service Rheumatology Respiratory | Review services currently being provided and to continue, where required, investment in and referrals to the service Work collaboratively with and across E&N Herts localities and secondary care to redesign improve and enhance the local services | Equitable service provided across Hertfordshire in a community setting and care closer to home agreed across all 7 localities | Locality leads | ongoing | Appropriate and equitable care closer to home Reduction in referrals to secondary care |
| Objective/Priority | Action | Milestones | Lead | Timescale | Outcome |
| Enhanced services Review existing enhanced services | Assess current GMS enhanced services to ensure they meet the needs of the locality and are within the allocated budget | Review of GMS enhanced services | Locality board | March 2009 | Ensure that services are provided for the needs of the population and within the ES budget allocation |
| Smoking cessation Continue to reduce numbers of people smoking in Welwyn Hatfield Locality | Commissioning NHS smoking cessation service to ensure rise in the number of quitters by Implementing a Smoking Cessation LES | National Quit Targets are met for each quarter | Executive Board | March 2009 | Numbers of quitters to rise each quarter |
| gynaecology The locality intends to introduce a major expansion of gynaecology services | By commissioning a Gynae LES | Planned reduction in referral to secondary care in line with ASR programme | Executive Board | March 2009 | Reduction in referral to secondary care |
| Neurology The locality will be reviewing local neuro service provision | Audit current services for patients within the locality with the aim to developing services locally | Reduction in referrals to out of area services | Executive Board | March 2009 | Patient service delivered in appropriate setting |
| Leg Ulcer services The locality will implement the delivery of community based Leg Ulcer services | Audit current leg ulcer patients; agree costs and provision locally; implement training for community nurses; source premises both in Welwyn & Hatfield areas | Reduction in GP/community nurse time, better services, closer to home for patients | Executive Board | March 2008 | Reduction in attendances in secondary care; realised GP time |
| Objective/Priority | Action | Milestones | Lead | Timescale | Outcome |
| Nursing Home provision Review nursing & residential provision | Audit current provision to identify any gaps in provision | Confirmation of appropriate service provision within the locality | Executive Board | March 2009 | Better care prevention management and enhanced services for patients in residential and nursing homes. Reduction in referral to secondary care |
| Patient participation Increase patient participation | Engage with service users to achieve full meaningful participation that reflects their expected experience To work towards a locality patient participation group to get truly patient focused services | Full engagement with all aspects of service redesign Locality wide patient participation group | Locality Board | March 2009 | Patient input into service redesign which will result in increased appropriate and timely community services closer to home |
| Provider Services Ensure adequate provision of nursing community services to meet demand and scope of services provided in the | Work with PCT provide services to review and contribute into provider services plans; agree the need for further Investment to ensure staffing levels are sufficient to deliver community nursing services, focusing on increased community matron provision | Adequate resources identified to implement development/provision of community services | Board and Provider Services | March 2009 | Patient satisfaction with a reduction in acute admissions activity and occupied bed days for the over 75s |
| Objective/Priority | Action | Milestones | Lead | Timescale | Outcome |
| Phlebotomy Equitable services across the locality | Review investment in phlebotomy services and work with the trust to achieve equality across the locality | Produce a LES service specification | Executive Board | March 2009 | Improved patient satisfaction and services locally |
| Performance & reporting Expand on current reporting mechanisms that informs local and national planning decision making | Work with PCT to produce accurate financial and patient activity Produce regular locality performance reports Develop forecasting techniques for commissioning Work with Public Health to use data to drive service redesign | Accurate monthly activity/financial reports feedback to locality and patient groups on a regular basis Locality based manager post recruited | Executive board | March 2009 | Information improvements will enable accurate monitoring and forecasting of current and future services. equitable access with a reduction in inequalities across its population |