West Herts Clinical Conclave

Action Points from meeting on 15 November 2007

| 1. | Members present Not available – to follow |  |
| --- | --- | --- |
| 2. | Intermediate care PBC groups leads identified:- Dacorum – Dr Gupta St Albans & Harpenden – advertised for rep Watford – Frances Kavanagh Hertsmere – Sue Simmonds & Nicolas Small WHHT – Jackie Pace to be involved Action: Sue Catnach to advise on medical input. Action: Clare Hawkins to advise 1st meeting date | SC CH |
| 3. | Urgent Care AAU operational policy to be circulated to PBC Urgent care leads for comment. Action: Lindsey Macintyre to send to Moira McGrath for circulation. WHHT running table top exercises – one internal on 18 Dec and event for wider stakeholders at end Feb Action: LM to identify date. PBC Leads to identify GPs to participate. Urgent Care Centre at Hemel – WHHT and PCT to discuss interim arrangements | LM LM/PBC leads DB/LM |
| 4. | Clinical Governance Group Colin Johnston & Sheila Borkett-Jones to establish clinical governance group. Action: PBC Groups to identify reps Dacorum – Richard Gallow already identified Action: PCT provider services to identify rep | SB-J/CJ PBC Leads KH |
| 5. | Terms of Reference SBJ and CJ felt that remit of group should be wider than service redesign & group should take into account workforce change and estates issues as well as service delivery. Subject to these changes, terms of reference were agreed. |  |
| 6. | Diabetes Needs to link to prescribing committee discussions. Timeline for project to be confirmed, subject to discussions at meeting on 19 Dec. Practices will review lists of current follow up patients and advise consultants. Full report back for Jan conclave | CJ/MW MW/MMcG PBC diabetes leads CJ/MW |
| 7. | Heart failure Steve Laitner to share draft pathway with John Bayliss. Formal service redesign group to be convened. PBC Leads:- Hertsmere – Harjeev Rai Dacorum – Corina Ciobanu St A & H – TBC Watford - TBC | SL |
| 8. | Map of Medicine SL to link with MoM re compatibility of different mapping products. PBC Groups to review possible use of MoM. | SL PBC Leads |
| 9. | Future meetings 12 Dec meeting to stay in. Future meetings to move to 3rd Thurs of month, ideally in Gurney or PP Lecture Theatre. Jackie Smith has booked. | JS |

MMcG 11/12/07