CHILDREN’S COMMISSIONING TEAM OPERATIONAL PLAN 08/09 draft

The operational plan has been developed to support the PCT achieve the improvements in children and maternity services set out in a range of policy including Maternity Matters, Every Child Matters, Aiming High for Disabled Children, NHS Operating Framework 2008/09 and the NSF.

| REF | OBJECTIVE | ACTIONS | OUTCOMES | TIMESCALES | PROGRESS |
| --- | --- | --- | --- | --- | --- |
| MATERNITY |
| JJ1 | Performance management of providers in meeting the action plans in place to achieve requirements of HCC and Maternity Matters | Trusts to share action plans Action plans with information on role of PCT and progress to Trust Boards Regular meetings with providers to assess progress against performance management framework and action plans | Measurable improvements to services identified and demonstrated Report to Board Trusts able to meet outcomes determined by HCC and Maternity Matters | Ongoing May 2008 Ongoing |  |
| JJ2 | Create and implement a performance management framework which allows providers to be measured against specific outcomes | Write framework document and populate with targets for 2008-9 Share and agree with stakeholders (commissioners, providers, MSLC) Sign off document and begin process of performance management | Usable document agreed by stakeholders PCT able to manage performance against agreed outcomes | April 2008 May 2008 |  |
| JJ3 | To develop the membership of the two MSLCs so that they are best able to support the performance management process | Consult with MSLCs on possibility of merging groups / encouraging closer working Commission training for MSLC membership Support MSLCs in developing work plans and in taking a more business like approach to meetings | MSLCs able to support commissioners in the performance management of providers. Membership has clear understanding of role and function MSLCs have appropriate membership – numbers and user engagement | March 2008 – Both MSLCs wish to remain separate but forget closer relationships Voices training - Sept 2008 End 2008 |  |
| JJ4 | To ensure that antenatal and newborn blood spot screening meet national guidelines | Work with local providers to implement Nuchal Translucency screening Identify barriers to implementation. Work with providers and public health team to performance manage issues. Identify cost pressures relating to screening services Work with local midwives and GPs to implement antenatal / postnatal shared care pathway to ensure timely referral etc. Attend and contribute to Herts newborn blood spot meetings | Nuchal Translucency screening provided to Hertfordshire women in a timely manner Cost implications recognised by PCT Children’s commissioning team representation | During 2008/9 Within SLA / increased investment for 2008/9 Ongoing |  |
| JJ5 | To work with commissioners and providers to develop a strategy for improvements to services for women with mental health problems during the antenatal / postnatal period | Link with other commissioners, maternity and mental health providers to map current provision against HCC report and NICE guidance and to identify gaps Establish working group to define care pathway Develop commissioning plan to implement care pathway | Strategy for improvements to services |  |  |
| JJ6 | Provide support to the review of Maternity Services in Hertfordshire as part of the Delivering Quality Healthcare for Hertfordshire Project | Organise review programme, liaise with providers and review team, collate information Take part in review during May 2008 Support the implementation of the review | Clear strategy for Maternity Services in Hertfordshire including low risk midwifery care | April 08 May 08 After Sept 08 |  |
| JJ7 | To develop a care pathway for maternity covering both the antenatal and postnatal provision | Develop draft pathway Discuss pathway with maternity services, GPs, PbC and LMC Agree care pathway Commissioning services to deliver agreed pathway | Agreed care pathway | April 08 June 08 Autumn 08 ongoing |  |
| JJ8 | To contribute the multi-agency Teenage Pregnancy strategy implementation | Represent PCT on TP partnership board (CP) Represent PCT on TP reference group (JJ) Ensure actions within the strategy are reflected in commissioning plans and service specification | TP rates continue to drop as per agreed trajectory and vital signs | Ongoing with quarterly monitoring |  |
| ACUTE CHILDREN |
| JJ9 | To ensure that the needs of children are taken into account in the process of developing urgent care services across Hertfordshire | Attend and participate in meetings and the selection and tendering process Obtain expert opinion where necessary and feed this into the process Feed back into commissioning team and wider PCT | Urgent care facilities take account of the specific needs of children and young people | Hemel Hempstead UCC - May 2008 Ongoing process across Hertfordshire |  |
| JJ10 | Take a lead role in supporting and facilitating providers to meet the 18 week referral to treatment targets including PCT provider services | Review commissioning team input into 18 week process Support and facilitate groups of providers from across health and CSF to review specific pathways | Providers are able to meet 18 week RTT targets across pathways | 18 week / models of care group reviewed, higher level group to be formed (April 2008) Work on ADHD and Allergy pathways underway Autism pathway work to be started – have spoken to PCT providers about this (April 2008) |  |
| JJ11 | Represent PCT on East and North Herts Women’s and Children’s reconfiguration groups | Attend and participate in meetings | Reconfiguration of services onto Lister site | Ongoing |  |
| JJ13 | To ensure that the developments of services on Local General Hospital sites includes where relevant children and maternity services | Identify potential opportunities for the development of children and maternity services that responds to DH and DFES policy | Agreed model for LGH includes children and maternity specifications | ongoing |  |
| JJ14 | To represent the PCT in the Beds and Herts Perinatal Network | Attend and participate in meetings |  | Ongoing |  |
| COMMUNITY CHILDREN INCLUDING PCT PROVIDER |
|  | To develop models for the provision of CDC services and link to capital programmes already in existence | Identify pathways or care for CDC Ensure work included in capital planning by PCT and LA | CDC development in E and N Herts Clear model for all CDC services | ongoing |  |
|  | To ensure service specifications in place for all service To ensure that the service specifications include integrated practice, children’s centres and extended schools | Agree with PbC groups their involvement in service specifications Draft to PbC Agree final version Send final version to provider | Specifications agreed with PbC groups and providers | ongoing |  |
|  | To ensure the implementation of the Child death review | Ensure implementation of protocol Ensure recruitment for rapid response and Designated Dr happens | Rapid response team in place Designated Dr in place | Ongoing review of implementation |  |
|  | Create and implement a performance management framework which allows providers to be measured against specific outcomes | Write framework document and populate with targets for 2008-9 Share and agree with stakeholders Sign off document and begin process of performance management | Usable document agreed by stakeholders PCT able to manage performance against agreed outcomes | June 2008 Sept 2008 |  |
|  | Develop a service specification for the provision of a dietetic service for children to include a service for children who are overweight or obese and children with an eating disorder | Agree investment with PbC | Agreed service specification and established children’s dietetic service | Sept 08 April 09 |  |
| CONTINUING CARE |
| RT/TC | Ensure the implementation of the children’s continuing care audit action plan | Audit action plan: Agree review process in county Agree review process for OOC Agree project plan for Continuing Care Database Agree process for reviewing matrix | Agreed review process Database defined and implemented |  |  |
| RT | To agree the SLA with Keech Cottage Hospice | Agree financial value of the SLA Agree activity profile for the SLA Implement regular SLA meetings with hospice | Signed SLA | May 08 |  |
|  | To align the commissioning of equipment and disposables for children with continuing care needs into the continuing care budget |  |  |  |  |
|  | Formalise the accountability framework for children’s continuing care | Regular meetings of the steering group Sign of draft accountability agreement | Signed accountability agreement |  |  |
|  | Create and implement a performance management framework which allows providers to be measured against specific outcomes | Write framework document and populate with targets for 2008-9 Share and agree with stakeholders Sign off document and begin process of performance management | Usable document agreed by stakeholders PCT able to manage performance against agreed outcomes | June 2008 Sept 2008 |  |
| CHILDREN WITH DISABILITY |
|  | To contribute to the joint planning of disability services for children | Attend JDSG Contribute to the service improvement plan | Ongoing May 08 |  |  |
|  | To develop a joint commissioning strategy for children with a disability on behalf of HCTP |  |  |  |  |
|  | To develop a participation strategy for children with a disability on behalf of HCTP |  |  |  |  |
|  | Contribute to the development of short breaks services for children with a disability | Agree framework for short breaks in conjunction with CSF through JDSG? Residential care review – ensure health input and consultation where necessary Attendance at Residential Respite Steering group meetings |  |  |  |
|  | Represent the PCT on the complex care panel |  |  |  |  |
|  | Represent the PCT on the complex care panel |  |  |  |  |
| TC | To develop children’s palliative care services in line with recent DH guidance |  | Children’s palliative care strategy with action plan |  |  |
|  | To ensure the effective commissioning of children’s equipment services |  |  |  |  |
|  | Bobath | Agree clinical criteria for referral Agree referral process and pathway Agree level of service for commissioning |  |  |  |
|  | Contribute to the development of transition services for 14-25 year olds |  |  |  |  |
|  | Work jointly with CSF on the commissioning of SALT services |  |  |  |  |
|  | Work jointly with CSF on the commissioning of OT services |  |  |  |  |
|  | Define the therapy contribution to special schools in Herts |  |  |  |  |
| EMOTIONAL HEALTH AND WELL-BEING INCLUDING CAMHS |
|  | To ensure the transfer of CAMHS commissioning from the JCPB to the HCTP under a section 10 agreement | Transfer to HCTP - details in place for transfer - Section 10 agreement - CYPP links/deliverables | Section 10 agreement in place |  |  |
|  | To ensure the development of a children’s emotional health and well-being strategy incorporating CAMHS strategy | Strategy development and launch develop new strategy 2 workshops Consultation process For ratification by CTPB Links/references to other docs such as CYPP | Children’s emotional health and well-being strategy with investment plan |  |  |
|  | Challenging behaviour | Challenging behaviour care pathways and service agreements development of new psychology posts transitions Behaviour Resource Service links Forest House Education/Day Service Provision Role of CAMHS in relation to LD/ASD Reprovision of HHCS LD service development Support to LD teams (CSF) from spec CAMHS |  |  |  |
|  | Tier 2 development | Early intervention and Prevention convene working group service mapping development of training prog development of partnership approach/integrated process |  |  |  |
|  | To develop a local approach to the commissioning of Eating disorder services | Eating disorder service models develop community service model monitor inpatient use training |  |  |  |
|  | To develop a participation and advocacy strategy for children and young people with emotional health and well-being needs |  |  |  |  |
|  | To commission a range of specialist services from CAMHS | Provision of specialist services – day, outreach and inpatient (incl Forest House) agreement with HPFT re service model develop service specification links to other services clear – BRS, Boxmoor |  |  |  |
|  | To ensure the emotional health and well-being needs of groups of vulnerable children are included in the commissioning of CAMHS services | Scope range of services for vulnerable children and young people. Agree resource/CAMHS support to: LAC LD EBD BME Parents with MH problems Sexualised behaviour Youth Offending |  |  |  |
| 3rd SECTOR COMMISSIONING |
|  | To jointly commission with CSF the specialist sexual abuse service from Treetops |  |  |  |  |
|  | To jointly commission with CSF Homestart services |  |  |  |  |
|  | To ensure projects funded by children’s fund are mainstreamed where relevant |  |  |  |  |
| VULNERABLE GROUPS |
|  | To ensure the commissioning of services for Looked After Children meets the statutory |  |  |  |  |
|  | Safeguarding including named GPs |  |  |  |  |
|  | To contribute to the multi-agency young carers work |  |  |  |  |
| GENERAL |
| CP | To be the HCTP ‘Being Healthy’ Lead and ensure the partnership meets the objectives set out in the JAR PIAP and CYPP |  |  |  |  |
| JJ12 DG | Represent PCT on Three Rivers and Welhat District and Children’s Trust Partnership Groups | Attend and participate in meetings, feedback into wider team and PCT | Representation at all DCTP groups | ongoing |  |
| CP | To ensure that the PbC groups in Hertfordshire are supported in the commissioning of children and maternity services | Share commissioning plan with PbC groups Attend leads meetings regularly and individual groups as invited Brief PbC groups on ‘must dos’ and agree commissioning actions | Agreement reached on commissioning plan for PCT provider services for 08/09 Improved understanding of children and maternity issues by PbC Inclusion of PbC reps in wider commissioning work | April 08 Ongoing April 08 |  |
|  | To continue the development of the commissioning team |  |  |  |  |
|  | to lead on the risk register for the directorate |  |  |  |  |
|  | To support the development of the patient experience and quality |  |  |  |  |
|  | To ensure that the annual child health mapping exercise is undertaken |  |  |  |  |
|  | To ensure that the learning from SUIs is embedded in commissioning plans and service specifications |  |  |  |  |
|  | To support the exceptional treatment process in relation to children |  |  |  |  |
|  | To support the transfer of NHSP services from ENHT to W Herts PCT |  |  |  |  |
|  | To contribute to regional work on children’s services via CSIP and regional commissioning network and the ESCG |  |  |  |  |