Review of progress against PBC DES objectives for DacCom PBC Ltd

Summary

The PBC DES for Dacorum was centred on achieving the Commissioning Plan which was drafted primarily by the PCT and agreed with DacCom Executive.  This Commissioning Plan primarily set out objectives relating to the PCT’s Financial Recovery Plan.  DacCom were not expected to achieve any priorities of their own but were expected to establish a robust governance structure for PBC in Dacorum.

Eight key objectives for DacCom have been identified as a result.  The level of achievement is set out in this document but in summary is as follows:

| Objective | % Achieved by DacCom | % not achieved due to DacCom | % not achieved due to PCT or other | Comments |
| --- | --- | --- | --- | --- |
| 1. Establish a robust and representative governance structure for PBC | 100% |  |  | Achieved |
| 2. Referrals management including clinical assessment services | 100% |  |  | Achieved within direction set and agreed with PCT |
| 3. COPD and Heart Failure service redesign | 30% |  | 70% | Stopped by new PCT |
| 4. Reduce Outpatient Follow ups | 100% |  |  | Achieved within direction set and agreed with PCT |
| 5. Urgent Care Centre | 40% |  | 60% | Stopped by old PCT |
| 6. Frequent Fliers Management | 30% |  | 70% | No clear direction set |
| 7. Prescribing budget | 100% |  |  | Heading for 1.75% overspend but achieved many switches |
| 8. Develop and write a business/commissioning plan for 2007/08 | 100% |  |  | Plans in place to achieve in full by first week April 07 |
| Total % achievement | 67% achievement |  | Represents 32% non achievement |  |
| Total achievement of 95p per patient | 64p per patient |  |  |  |

1. Establish a robust and representative governance structure for PBC

| Task | Responsibility | Date Achieved or reasons why not achieved |
| --- | --- | --- |
| Agree an appropriate structure acceptable to member practices, PCT and DacCom |  | DacCom with PCT support | Yes |
| Establish an Executive Committee elected by member practices with identified leads with specific responsibilities |  | DacCom | Yes |
| Secure maximum sign up from local practices |  | DacCom with PCT support | Yes |
| Establish a mechanism for the Executive to report to and be held to account by the member practices |  | DacCom with PCT support | Yes – Locality meetings and “Hot Topics” |
| Establish the corporate governance arrangements |  | DacCom | Yes – incorporated as a limited company with directors |
| Put in place agreements with all practices |  | DacCom | Yes |
| Agree a commissioning plan with the PCT reflecting the priorities of the PCT | PCT management with DacCom support |  | Yes |
| Establish and hold regular business meetings to plan and deliver agreed objectives |  | DacCom | Yes – monthly meetings held and minuted with regular progress reports |

Relevant notes:  DacCom achieved 100% of the tasks identified within this objective.

2. Referrals management including clinical assessment services

| Task | Responsibility | Date Achieved or reasons why not achieved |
| --- | --- | --- |
| Agree an approach to referral management following an option appraisal |  | DacCom with PCT support | Yes |
| Develop a project plan for the initiative | PCT management with DacCom support |  | tbc |
| Ensure broad GP ownership of the initiative |  | DacCom with PCT support | Yes |
| Letter sent out with agreed format for weekly data collection and reporting |  | DacCom with PCT support | Yes - MM |
| All practices submit data on a monthly basis on referrals |  | DacCom with PCT support | Yes |
| Issues highlighted and resolved within practices and DacCom |  | DacCom with PCT support | Yes |
| Information collated and sent out to practices | PCT management |  | Yes - PP |
| Information report provided to DacCom Executive | PCT management |  | Yes - tbc |
| Reduction of 10% of referrals in top 8 specialties |  | DacCom with PCT support | Yes |
| Review and consider next steps |  | DacCom with PCT support | Yes – tbc |

Relevant notes:

DacCom achieved 100% of the tasks identified within this objective.

3. COPD and Heart Failure service redesign

| Task | Responsibility | Date Achieved or reasons why not achieved |
| --- | --- | --- |
| Develop a project plan for the initiative | PCT management with DacCom support |  | Yes - tbc |
| Ensure broad GP ownership of the initiative including through “Hot Topics” group |  | DacCom with PCT support | Yes |
| Draw up service specifications for the initiative liaising with other professionals as necessary in line with Investing in Your Health approach |  | DacCom with PCT support | Yes |
| Circulate proposed new pathways to all practices for information and discussion |  | DacCom with PCT support | Yes |
| Undertake financial/activity analysis, assess viability and agree a commissioning process to select preferred provider | PCT with DacCom support |  | Stopped by new PCT at this stage |
| Carry out a commissioning process – select preferred provider | PCT with DacCom support |  |  |
| Ensure production of service proposals as part of the commissioning process | PCT through preferred provider |  |  |
| Undertake a financial analysis of the proposals, negotiate finances/activity and make recommendations | PCT management |  |  |
| Submit recommendations to PCT Directors for approval once ready | PCT management |  |  |
| Once agreed, communicate to GPs to ensure service used appropriately |  | DacCom with PCT support |  |
| Ensure monitoring system in place to determine the success of the service | PCT management with DacCom support |  |  |
| Once project starts monitoring carried out and reported by provider to PCT and then by PCT to DacCom | PCT management |  |  |
| DacCom to keep practices informed of progress – receive feedback and make recommendations for service changes as necessary |  | DacCom with PCT support |  |
| Other tasks involved |  |  |  |

Relevant notes:  DacCom achieved 30% of the tasks identified within this objective – the remaining 70% needed PCT action prior to full implementation.

4. Reduce Outpatient Follow ups

| Task | Responsibility | Date Achieved or reasons why not achieved |
| --- | --- | --- |
| Agree approach and lead responsibilities |  | DacCom with PCT | Yes – TF & JK |
| Practices sent list of their patients due to have follow up appointments in next 6 months |  | DacCom with PCT support | Yes |
| Practices checked and notified Monica Hough regarding all patients not needing follow ups who could be discharged |  | DacCom | Yes |
| Monica to follow through with WHHT | PCT Management |  | Yes – tbc MH |

Relevant notes:

DacCom achieved 100% of the tasks identified within this objective.

5. Urgent Care Centre

| Task | Responsibility | Date Achieved or reasons why not achieved |
| --- | --- | --- |
| Develop business case | PCT with DacCom support |  | Yes – as part of the FRP |
| Develop action plan | PCT with DacCom support |  | Yes – within the FRP |
| Undertake financial and activity modelling and viability analysis | PCT with DacCom support |  | Yes – within the FRP but limited |
| Develop DacCom model for a UCC |  | DacCom with PCT support | Yes – J Cohen and M Jones |
| Secure support from local practices – paper presented to DacCom and “Hot Topics” |  | DacCom with PCT support | Yes |
| Secure PCT approval and give notice on SLA | PCT with DacCom support |  | No – stopped by PCT at this stage |
| Work with West Herts PBC Leads to progress this |  | DacCom with PCT support | Yes - ongoing |
| Develop West Herts model of service and service specification | PCT with DacCom support |  | Currently underway |
| Consult on service specification | PCT with DacCom support |  | To do |
| Develop criteria for assessing proposals | PCT with DacCom support |  | To do |
| Agree procurement process | PCT with DacCom support |  | To do |
| Secure agreement of local practices to the service specification, criteria and procurement process |  | DacCom with PCT support | To do |
| Undertake procurement process | PCT with DacCom support |  | To do |

Relevant notes:  DacCom achieved 40% of this tasks identified within this objective – the remaining 60% needed PCT action prior to full implementation.

6. Frequent Fliers Management

| Task | Responsibility | Date Achieved or reasons why not achieved |
| --- | --- | --- |
| Establish business case | PCT with DacCom support |  | No clear steer appears to have been given yet |
| Establish project plan | PCT with DacCom support |  | No project plan yet |
| Validate data and report back to Lynn Dalton on which frequent fliers could be managed differently – found most dead as data out of date, others very sick or in need of more DN support |  | DacCom | Yes |

Relevant notes:  DacCom achieved 30% of the tasks identified within this objective due to lack of clear business case and project plan setting out what needed to happen.

7. Prescribing budget

| Task | Responsibility | Date Achieved or reasons why not achieved |
| --- | --- | --- |
| Agree areas for action – Prescribing plan |  | DacCom with PCT support | Yes – tbc RG |
| Secure ownership of plan by wider GP body |  | DacCom with PCT support | Yes – tbc RG |
| Monitor achievement against plan |  | DacCom with PCT support | Yes – tbc RG |
| Review plan and consider any additional in year priorities |  | DacCom with PCT support | Yes – tbc RG |
| Implement any agreed additional in year priorities |  | DacCom with PCT support | Yes – tbc RG |

Relevant notes:  DacCom achieved 100% of the tasks identified within this objective.

Medicines Management performance markers show that DacCom practices’ prescribing performance compares well with the rest of Hertfordshire although the budget is heading for an overspend of 1.75%.

8. Develop and write a business/commissioning plan for 2007/08

| Task | Responsibility | Date Achieved or reasons why not achieved |
| --- | --- | --- |
| Establish project group |  | DacCom with PCT support | Yes |
| Agree vision and values and key objectives with member practices within PCT framework |  | DacCom with PCT support | Yes |
| Produce first draft for discussion with member practices |  | DacCom with PCT support | Planned March |
| Discuss with member practices |  | DacCom | Planned March |
| Review and amend as necessary and agree with practices |  | DacCom with PCT support | Planned March |
| Secure agreement of PCT Directors/PBC Governance Committee | PCT management with DacCom support |  | Planned April 3 |
| Develop project plans for key initiatives to meet objectives | PCT management with DacCom support |  | Planned March |

Relevant notes:  DacCom has a project plan to achieve 100% of the tasks identified within this objective by the first week of April 07.