East and North Herts

Record of Business Cases approved by the PBC Governance Sub-Committee

This table represents the business cases that have been presented at the PBC Governance Sub-Committee since the Committee was first established in March 2007.

| Date of Meeting | Locality /PBC Group | Business Case | Comments | Date Approved | Date Service Commenced |
| --- | --- | --- | --- | --- | --- |
| March 07 | East Locality | Orthopaedics Care Pathway | Approved LES with South Street Practice. Practice and SLA for Triage with WE PCT. Service commenced June 2007. | March 07 | June 2007 |
|  | East Locality and West & Central Locality | Direct Access to Echocardiography (PAH) | Agreement with PAH from March 2007 | March 07 | May 2007 |
| April 07 | No Business Cases approved during this month |  |
| May 07 | No Business Cases approved during this month |  |
| June 07 | No Business Cases approved during this month |  |
| July 07 | Welwyn & Hatfield Locality | Rheumatology | MSK (including rheumatology) pathway, currently under the management of PCT provider services. Current GPwSI seeing secondary care patients under the clinical supervision of Consultant Jeremy Axon; invoices from the GP practice are now forwarded to PCT provider services for payment. | Never commenced – will remove from records | N/A |
|  | South Locality | ENT | Approved AWP with Dr Achiriga. Service Commenced 11th February 2008. | July 07 | Feb 08 |
|  | East & North Herts Commissioning Groups | Oxygen Therapy | Withdrawn in August | N/A | N/A |
|  | South, East, North and West & Central Localities | Beating the Blues LES | Approved LES with Cromwell Medical Centre; service commenced September 2007 | July 07 | Sept 07 |
| August 07 | South Locality | Phlebotomy Business Case | Approved SLA with Provider Services; start date still to be finalised | August 07 | Planned for May 2008 but unable to recruit staff |
|  | Prescribing Team | Medicines Waste Management | Approved | December 07 | December 2007 |
| October 07 | No Business Cases approved during this month |  |
| December 07 | No Business Cases approved during this month |  |
| January 08 | No Business Cases approved during this month |  |
| April 08 | North Herts | Primary Care Cardiology services (AF Pathway) | Approved | April 08 | Tbc |
|  | Stevenage Locality | Drug Misuse Service in Stevenage | Approved | April 08 | Tbc |
|  | Stevenage Locality | Alcohol Misuse Misuse Service in Stevenage | Approved | April 08 | Tbc |
|  | West & Central | Provision of Clinical Monitoring of Coeliac Disease | Provisionally approved as a Pilot Scheme | April 08 | Tbc |