Draft

THE MOUNT

LOCAL PRISON HEALTH DELIVERY PLAN

Introduction

The Local Prison Health Delivery Plan (LPHDP) has been developed in partnership between HMP The Mount and Dacorum PCT, following guidance issued by the Home Office and the Department of Health.  It also draws on a variety of additional sources as follows:

Health Needs Assessment Action Plan (HNAAP) HMP The Mount Business Plan 2003-4 (TMBP)

SAU Action Plan  (SAUAP)

Prison Service Independent Monitoring Board Annual Report January 2003 to February 2004 (IMBAR)

Local Partnership Workshop – HMP The Mount and Dacorum PCT

A Partnership Board has been established to oversee the implementation of the LPHDP for 2004-5 recognising the interdependence of the Prison and the PCT in the delivery of services to prisoners. Terms of reference and membership are included in Appendix 1.  Through the continued development of the LPHDP in future years the Partnership Board has responsibility for improving the provision of health care services for prisoners, and is accountable to both the PCT and Prison Governor, representing the dual responsibility that is held by the PCT Chief Executive and HMP The Mount’s Governor.

The LPHDP is divided into sections:

- Primary Care

- Mental Health

- Pharmacy

- Dentistry

- Health Promotion

- Substance Misuse

- Communicable Disease

- Workforce Development

- Policies and Procedures

- Health and Safety.

The actions recommended within the LPHDP are underpinned by the following principles:

- Prisoners are entitled to have access to the same range of services as the community within which the prison is based

- The quality of services should be equitable to those available to the local community

- The environment in which services are provided should be of the same standard as that in which other local services are provided.

- The services are provided within the PCT clinical governance framework

- The LPHDP is the framework by which health services are provided to  prisoners and is part of a dynamic process of improvement

# PRIMARY CARE

| Reference | Target | Action | By when | Lead | Monitoring arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
| LPW | Ensure primary care provision in line with nGMS contract and meeting the requirements of the prison service | Seek advice from PCT IT manager on appropriate system for prison healthcare. | October 2004 | Healthcare manager/PCT Acting Chief Executive |  |
| LPW |  | Purchase and populate the IT system. | March 2004 | PCT IT manager/Healthcare manager |  |
|  |  | Review health needs | May 2005 | Healthcare manager/PCT public health department |  |
| SAUAP 55.9, 61.2 & 61.7 |  | Review what and where services are provided including requirements to examine prisoners at reception, in segregation, where force has been used to restrain a prisoner, and where a prisoner is in special accommodation or mechanical restraints | June 2005 | Healthcare manager | Monthly audits |
|  |  | Agree and undertake programme of audits in line with PCT clinical governance guidelines | April 2005-6 |  |  |
|  |  | Provide information to prisoners on services available and how they are accessed | August 2004 | Healthcare manager | Achieved |
| LPW | To ensure prisoners have access to secondary care via the healthcare centre where possible | Explore alternative ways of accessing specialist support e.g. telemedicine, enhanced services |  |  |  |
|  |  | Contact local GP with experience of telemedicine | September 2004 | PCT Primary care Manager |  |
|  |  | Explore options in further detail | 2005/06 | PCT Primary care Manager/ Commissioning Manager/ Healthcare Manager |  |

# MENTAL HEALTH

| Reference | Target | Action | By when | Lead | Monitoring arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
| LPW | Provision of mental health services to meet the assessed needs of prison population | Health needs analysis to be undertaken | September 2004 | Healthcare manager & HPMHT (should we say the position?) |  |
| LPW |  | Review existing services and identify gaps | October 2004 | Healthcare manager & HPMHT |  |
| HNAAP |  | Agree how existing skills/services are to be used | October 2004 | Healthcare manager & HPMHT |  |
| LPW |  | Develop costed proposal for meeting gaps in service | December 2004 | HPMHT | Agree proposals with Healthcare manager and Healthcare Governor. Follow PCT process for commissioning discussions |
| LPW |  | Agree service specification with PCT | Early March 2005 | PCT supported by HPMHT and Healthcare manager | Agree eligibility criteria as an integral part of specification |

# PHARMACY

| Reference | Target | Action | By when | Lead | Monitoring arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
| LPW | Agree a prison drugs strategy | Review current and future provision of pharmacy service based on need | July 2004 | Regional Pharmacy Advisor | Achieved |
|  |  | Agree action plan to implement the prison drug strategy | August 2004 | PCT/Governor |  |
| LPW |  | Pharmacy service to be commissioned | April 2005 | PCT | Project manager appointed to support commissioning |
|  |  | Service specification to be agreed | December 2004 | PCT | Project manager appointed |
| LPW |  | PCT to take on responsibility for provision of pharmacy service | April 2005 | PCT Head of Medicines Management | Process for recruiting a pharmacist is underway |
| SAUAP |  | Local prescribing formulary to be developed | September 2004 | Healthcare manager/PCT Medicines Management Manager | Achieved |
| LPW |  | Agree policy on ‘in possession’ medication including risk assessment tool and implement policy | April 2005 | Healthcare Manager/PCT Medicines Management Manager |  |
| TMBP |  | Ensure current agreement with HMP Chelmsford is complied with | July 2004 | Healthcare manager/Function head | Monthly audit reports |
| SAUAP 22.31 | Policy on access to simple analgesia and antacids in the absence of healthcare staff to be produced |  | September 2004 | Healthcare Manager | Actioned |

DENTISTRY

| Reference | Target | Action | By when | Lead | Monitoring arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
|  | Dental services to be reviewed to reflect identified need | Needs assessment to be undertaken | December 2004 | Healthcare manager |  |
| SAUAP 22.33 |  | Waiting time for emergency treatment to be reduced | September 2004 | Healthcare manager | Improvements already made to appointments system |
| SAUAP |  | DNA rates to be improved | December 2004 | Healthcare manager | Improvements already made in appointments system and joint working with prison officers |

# HEALTH PROMOTION

| Reference | Target | Action | By when | Lead | Monitoring Arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
|  | Develop health promotion strategy based on assessed needs | Set up multi-disciplinary health promotion group with prisoner involvement | October 2004 | Healthcare manager/PCT health promotion department | Prisoner on the group will report back to Prisoner Representative Group |
| TMBP |  | Establish health promotion clinics to line with relevant NHS National Service Frameworks (NSFs) eg Smoking cessation | On-going programme from April 2004 to March 2005 | As above | Monthly reports to Function Head |
|  |  | Work in partnership with kitchens to improve nutritional content of meals offered in the canteen and ‘signpost’ to healthy options | August 2004 for diabetic prisoners | Healthcare manager/Catering Manager | Further signposting to be considered |

# SUBSTANCE MISUSE

| Reference | Target | Action | By when | Lead | Monitoring arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
|  | Ensure prison drug strategy is compatible with Dacorum drugs strategy | Link with other agencies who have responsibility for the provision of drug misuse services | September 2004 | PCT Director of Public Health |  |
| SAUAP 10.2 |  | Assess local needs and identify gaps in services |  |  |  |
|  |  | Integrate PCT services with prison services | September 2004 | PCT Primary Care Manager |  |
|  |  | Look at options for using PCT enhanced services to augment existing prison service | December 2004 | PCT Primary Care Manager |  |
|  | Increase the number of prisoners with ‘compact’ for remaining drug free | All prison wings to have a designated nurse | March 2005 | Healthcare manager |  |
| SAUP | Ensure prisoners have access to the CARATS service | Staff to refer prisoners who are identified as having a drug related problem/issue to CARATS for assessment |  |  |  |

# COMMUNICABLE DISEASE

| Reference | Target | Action | By when | Lead | Monitoring Arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
| LPW | Ensure prisoners are up to date with vacc and imms | Review system for Hepatitis B | November 2004 | Healthcare manager |  |
|  |  | All ‘at risk’ prisoners to be identified and offered flu vaccine | Healthcare manager | November 2004 |  |
|  | Review sexual health services |  | Healthcare manager/Project manager | October 2004 |  |
|  |  | Ensure all prisoners have access to sexual health services | Healthcare manager | November 2004 |  |
| LPW | Ensure all policies are updated | Link with Health Protection Agency and local infection control group | Healthcare Manager | January 2005 | Healthcare Manager already attending local infection control group |

# WORKFORCE DEVELOPMENT

| Reference | Target | Action | By when | Lead | Monitoring arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
| LPW | Ensure appropriately qualified and trained staff are employed to provide services | Skill mix review of current staff | July 2004 | Healthcare manager | Completed and vacancies filled |
| LPW | Adopt PCT Life Long Learning Policy | Develop appraisal system for all staff | April 2005 | Healthcare manager |  |
|  |  | Ensure Personal Development Plans are in place for all nursing staff |  |  |  |
|  |  | Appropriate training is in place to support health care objectives |  |  |  |
|  |  | Ensure study leave is fair and equitable and supports health care and prison objectives |  |  |  |
|  |  | Provide support and mentoring for nursing staff |  |  |  |
| LPW | Comply with PCT Agenda for Change | Agree action plan | ?? | Healthcare Manager/Human Resources |  |
| LPW | Increase number of clinical placements | Adopt PCT clinical placement policy | ?? | Healthcare Manager |  |
| LPW | Agree a change management programme | Ensure change management programme is implemented |  | Healthcare Manager/PCT | Agree how baseline is established and a process for outcomes of the change management programme are audited |
| TMBP | Ensure that all staff are trained and adhere to Prison Service policy for Race Relations and Equal Opportunities |  | ?? | Healthcare Manager/Function Head |  |

# POLICIES AND PROCEDURES

| Reference | Target | Action | By when | Lead | Monitoring arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
| SAUAP 22.13 22.15 | Medical records to be of good quality and accessible to prisoners | To summarise records and enter on clinical system | April 2005 | Healthcare Manager | Use Quality and Outcomes Framework process for monitoring |
|  |  | Agree a policy for prisoner access to records | September 2004 | Healthcare Manager | Actioned |
| LPW | All service providers to enter information on clinical systems | Agree a policy | April 2005 | Healthcare Manager/in reach service providers |  |
| SAUAP 22.9 | A policy statement on intimate physical examination to be produced |  | September 2004 | Healthcare Manager | Actioned |
| SAUAP 22.22 | This is an unclear recommendation – can it be clarified? |  |  |  |  |
| SAUAP 6.3 6a | To adopt the NHS complaints procedure | To assess how the NHS complaints procedure meets the recommendations of the SAUAP | April 2005 | Healthcare Manager/Function Head |  |

# ENVIRONMENT/HEALTH AND SAFETY

| Reference | Target | Action | By when | Lead | Monitoring arrangements/Comments |
| --- | --- | --- | --- | --- | --- |
| SAUAP 22.7 | Access to the healthcare centre for disabled prisoners to be improved | For discussion at EC level |  |  |  |
| SAUAP 21.10 | Health and Safety rules for all equipment must be displayed with the equipment including X ray machines | Regularly review to ensure up top date advice is complied with | Throughout the year | Healthcare Manager/Health and Safety Officer |  |
| SAUAP 10.2 | Procedure to prevent drugs entering the prison via the perimeter | Drug strategy to be comprehensively reviewed | July 2004 | Prison Governor | Capital bid to be made to improve the perimeter fence |
| LPW | Increase drug free accommodation | Develop a bid for the Partnership Board to extend RAPT programme | October 2004 | Deputy Governor |  |
| SAUAP 54.119 54.123 | The Prison must assess the physical security of NHS service providers where prisoners are referred for out patient and in patient treatment | Review to be undertaken | August 2004 | ?? Titles | Completed and Governor’s Order 27/04 issued |