Appendix C

Primary Care Access and Responsiveness –

East & North Herts and West Herts PCT - Action plan

Analysis and Diagnosis – Short term

|  | Proposed action | Progress | Lead | Timescale |
| --- | --- | --- | --- | --- |
| Identifying poorly performing practices | Carry out analysis of survey results using SHA averages and Des minimum % requirements as benchmarks to identify poorly performing practices | Practices not achieving the minimum and also the SHA average for the 4 categories have been identified | Primary Care Commissioning | By 7th September 2007 |
|  | Analysis of the full responses for all categories to identify in more detail patients perspectives |  |  | End of October 2007 |
|  | Meeting with Director of Primary Care Commissioning and other key members of PCT to discuss findings | Meeting to be held on 11th September |  |  |
| Identify Broader trends across PCT | Carry out in depth analysis of results to identify any trends between practices relating to ethnicity, age, gender, deprivation, rurality, frequency of attendance etc. Identify other sources of information that could be included in this analysis |  |  | End of October 2007 |
|  | Identify other sources of information that can be used to give a fuller picture of practices |  |  |  |
| Identification of underlying causes of problems | For those practices identified as under performing identify staffing levels, list sizes, Liaise with other PCT colleagues (eg PBC leads, Public health) to identify any underlying problems (eg patient population issues, OOH provision etc) |  |  | End of October 2007 |
|  | Produce a report for the PCT Directors, Board and Executive committees outlining the PCTS performance and proposed action plan | Draft to be produced for September 2007 meeting and full report for October 2007 meeting. Update to be given quarterly as required |  |  |

Translating analysis into Actions – Short term

|  | Proposed action | Progress | Lead | Timescale |
| --- | --- | --- | --- | --- |
| Outline specific actions for individual practices | Arrange meetings with all poorly performing practices to discuss Access. At these meetings an action plan will be drawn up and agreed for the coming year | Meetings currently being arranged |  |  |
|  | Individual practice action plans to be monitored against agreed milestones on a quarterly basis |  |  | On going |
|  | Where appropriate information to be shared with PCT PBC leads to help support the work |  |  | On going |
|  | Meet with individual PBC localities to help identify solutions for specific issues |  |  |  |
|  | Identify any practices that are restricting or limiting bookings and focus on ‘remedying’ these actions. Also sharing good practice found in other practices and PCT areas |  |  |  |
| Outline any PCT wide plans | Following initial analysis any trends identified will be examined further. Where necessary produce plans to deal with specific issues. This may include OOH provision, deprivation, enhanced service provision |  |  |  |
|  | At any GMS and PMS review meeting access to be included as an agenda item |  |  |  |
|  | Identify links to PCT complaints, PALs etc to input ‘soft’ information on any access problems |  |  |  |
|  | Share good practice across the area in particular focusing on advance booking and contingency planning |  |  |  |
|  | Look at communications – identify how patients receive information about a practices appointment system |  |  |  |
|  | Look at the skill mix available across the localities – is the best use being made of other health professionals such as pharmacists |  |  |  |
| Define key actions, milestones and measures of success |  |  |  |  |

Medium term strategy – issues to consider

|  | Proposed action | Progress | Lead | Timescale |
| --- | --- | --- | --- | --- |
| Fairness in Primary care | Although GMS contract does not specify required staffing levels it may be necessary to try and identify if any practice is ‘under doctored’. Depending on the outcome of this analysis further work may be necessary. | As part of the QoF work an analysis is due to take place to compare list sizes and staffing levels |  |  |
| Contestability and choice in primary care | Identify if there are any restrictions on registering. Identify which practices have closed lists and which have applied or are likely to apply in the near future, which are requesting changes to their boundaries, etc.. If necessary work may be carried out to identify and model what new services are required possibly via APMS, SPMS etc |  |  |  |
| Premises | Identify which practices have a problem with their premises | A county wide premises/estates strategy is currently being drawn up to identify issues for premises development in the future | PBC groups, premises team, strategic planning | January 2008 |
| Use of additional investment to optimise access | If it is found that there is a need for additional access a case will be drawn up and presented to the Executive for consideration |  |  |  |
| Use of GMS/PMS contractual annual review to improve access | At any GMS and PMS review meeting access to be included as an agenda item | Practices currently being identified for Annual review meetings | Primary Care Commissioning | On going |