Last Meeting:	Friday 30 March 2007	attended by:

| Mark Jones | Suzanne Novak | Christine Walden |
| --- | --- | --- |

Next Meeting:	To be arranged

Project Milestone Report:

Current Actions:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 001 | CW | Task Michelle to organise a schedule of meetings for the Programme Management Group | 5 Apr 07 | Identified 30 Mar 07 |
| 002 | CW | Establish a process to identify sponsors for DacCom Exec meetings | 13 Apr 07 | Identified 30 Mar 07 |
| 003 | SN | Secure PbC Governance Sub-Committee agreement to the Business Plan for 2007/8. | 3 Apr 07 | Identified 30 Mar 07 We have submitted a draft plan. We intend this to be a working document to be updated as new projects are defined. |
| 004 | MJ | Provide Feedback to Andrew Parker regarding the Commissioning Framework. | 5 Apr 07 | Identified 30 Mar 07 |
| 005 | SN | Secure funding for DacCom at Level 3 in the Commissioning Framework. | 3 Apr 07 | Identified 30 Mar 07 We will propose interim funding at this level based on progress to date. |
| 006 | CW | Determine whether the document developed by WatCom can be used as a basis for our agreements with the Practices. | 5 Apr 07 | Identified 30 Mar 07 |
| 007 | CW | Secure progress of COPD Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 |
| 008 | CW | Secure progress of Heart Failure Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 |
| 009 | MJ | Work with Dorothy Pluck to secure progress of Counselling Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 |
| 010 | MJ | Work with Sandy Gower to secure progress of Physiotherapy Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 |
| 011 | MJ | Identify clinical leads and management leads for projects: Community Nursing Prescribing Referral Management Diabetes | 30 Apr 07 | Identified 30 Mar 07 |
| 012 | MM | Identify actions to deliver the Company AGM. | 31 May 07 | Identified 30 Mar 07 |

Next action 013