Last Meeting:

Wednesday 18 April 2007

Attended by:

| Mark Jones | Mary McMinn | Suzanne Novak |
| --- | --- | --- |

Apologies:

| Christine Walden |  |
| --- | --- |

Next Meeting:

Friday 4 May 2007 @ 11.30 am at Fernville Surgery

Project Milestone Report:

Decisions:

- Milestone 1 is achieved for the COPD project

- Actions arising are listed below (actions 015, 016, 017)

Actions closed in this report:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 001 | CW | Task Michelle to organise a schedule of meetings for the Programme Management Group | 5 Apr 07 | Identified 30 Mar 07 Complete 18 Apr 07 We will meet at 11.30 before each Executive Committee meeting, at least until fatigue defeats us. |
| 002 | CW | Establish a process to identify sponsors for DacCom Exec meetings | 13 Apr 07 | Identified 30 Mar 07 Complete 18 Apr 07 Chris will try to find a sponsor for each meeting and will give Mark 24 hours notice if this cannot be done. In this case, Fernville will provide lunch and invoice the PCT via DacCom to recover the cost. |
| 003 | SN | Secure PbC Governance Sub-Committee agreement to the Business Plan for 2007/8. | 3 Apr 07 | Identified 30 Mar 07 We have submitted a draft plan. We intend this to be a working document to be updated as new projects are defined. Complete 3 Apr 07 This was reviewed by the sub-committee on 3 April. It is not clear that any further review is expected, other than review of business plans for individual projects. |
| 004 | MJ | Provide Feedback to Andrew Parker regarding the Commissioning Framework. | 5 Apr 07 | Identified 30 Mar 07 Complete 18 Apr 07 Mark provided a summary by e-mail, which was acknowledged. However, the PCT Board has approved the Framework, so we will address the requirements as currently formulated. |
| 005 | SN | Secure funding for DacCom at Level 3 in the Commissioning Framework. | 3 Apr 07 | Identified 30 Mar 07 We will propose interim funding at this level based on progress to date. Complete 3 Apr 07 Funding has been approved at Level 3 to end-June. At this point we will have to confirm our achievement of Level 3 objectives. See action 013. |
| 006 | CW | Determine whether the document developed by WatCom can be used as a basis for our agreements with the Practices. | 5 Apr 07 | Identified 30 Mar 07 Complete 18 Apr 07 Mark has drafted an agreement for Dacorum practices building upon (and improving on) the WatCom model. |
| 007 | CW | Secure progress of COPD Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Complete 18 Apr 07 |

Ongoing Actions:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 008 | CW | Secure progress of Heart Failure Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 |
| 009 | MJ | Work with Dorothy Pluck to secure progress of Counselling Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. |
| 010 | MJ | Work with Sandy Gower to secure progress of Physiotherapy Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. |
| 011 | MJ | Identify clinical leads and management leads for projects: New Dacorum Hospital Enhanced Services Community Nursing Prescribing Referral Management - done Diabetes | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 The action has been modified to maintain alignment with the Business Plan. |
| 012 | MM | Identify actions to deliver the Company AGM. | 31 May 07 | Identified 30 Mar 07 Status 18 Apr 07 Mary has asked Richard Walker for the date of the next Hot Topics Meeting, which could be a vehicle for the AGM. |
| 013 | MJ | Demonstrate DacCom’s achievement of Level 3 objectives to the PbC Governance Sub-Committee. | 30 Jun 07 | Identified 18 Apr 07 |
| 014 | MJ | Coordinate practices’ sign-up to the PbC LES. Send papers to the practice managers by e-mail and ask Michelle to send hard copy to the practices. | 11 May 07 | Identified 18 Apr 07 |
| 015 | CW | Add any readily available detail to the section “consultation with stakeholders” in the Milestone 1 report for the COPD project. | 30 Apr 07 | Identified 18 Apr 07 |
| 016 | CW | Develop a costed business case for the COPD project and submit this to the PbC Governance Sub-Committee. | 31 May 07 | Identified 18 Apr 07 |
| 017 | MM | Review with Gerry Bulger the possibility that Dacorum Health could be the vehicle for delivering the redesigned COPD service under the Willing Provider model. | 30 Apr 07 | Identified 18 Apr 07 |
| 018 | MJ | Enrol Sapana Sheth as project manager for the Prescribing project. | 30 Apr 07 | Identified 18 Apr 07 |
| 019 | CW | Identify the budgets for Mental Health Services & Counselling and communicate these to Richard Gallow. | 30 Apr 07 | Identified 18 Apr 07 |
| 020 | MJ / SW | Facilitate a meeting of those involved in the Counselling project to ensure roles and deliverables are clear. | 11 May 07 | Identified 18 Apr 07 |

Next action 021