Last Meeting:

Wednesday 23 May 2007

Attended by:

| Mark Jones | Suzanne Novak | Christine Walden |
| --- | --- | --- |

Apologies:

| Mary McMinn |  |  |
| --- | --- | --- |

Next Meeting:

Thursday 7 June 2007 @ 11.00 am at Fernville Surgery

Project Milestone Report:

Decisions:

- Future meetings will commence at 11am and we will invite all management leads to attend.

- Other decisions are recorded in the action list below.

Actions closed in this report:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 015 | CW | Add any readily available detail to the section “consultation with stakeholders” in the Milestone 1 report for the COPD project. | 30 Apr 07 | Identified 18 Apr 07 Complete 23 May 07 Mark has added the revised version to the file. |
| 024 | MM | Seek input from Richard Walker to ensure progress on the New Dacorum Hospital Project. | 11 May 07 | Identified 4 May 07 Closed 23 May 07 A meeting was attended by MM and RW on 15 May and minutes circulated. Comments are required from Executive members to feed back to the next meeting. |
| 025 | MJ | Work with Trevor Fernandes to define a project plan for the 2007/8 LES programme. | 23 May 07 | Identified 4 May 07 Complete 21 May 07 Sue Rivers-Brown has been identified as the management lead. Mark has discussed a plan with Trevor and communicated this to Sue. We now expect to put the project through the Milestone process. |

Ongoing Actions:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 008 | CW | Secure progress of Heart Failure Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 4 May 07 It would be helpful to build confidence in the process to Milestone 2 before putting this project through Milestone 1. So this action will follow action 021. |
| 009 | MJ | Work with Dorothy Pluck to secure progress of Counselling Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. |
| 010 | MJ | Work with Sandy Gower to secure progress of Physiotherapy Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. |
| 011 | MJ | Identify clinical leads and management leads for projects: New Dacorum Hospital - done Enhanced Services - done Community Nursing Prescribing – done Referral Management - done Diabetes – done | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 The action has been modified to maintain alignment with the Business Plan. Status 4 May 07 We now have confirmed leads for most items. Mark has asked all GPs for a volunteer to lead for Community Nursing but has had no response. |
| 012 | MM | Identify actions to deliver the Company AGM. | 31 May 07 | Identified 30 Mar 07 Status 18 Apr 07 Mary has asked Richard Walker for the date of the next Hot Topics Meeting, which could be a vehicle for the AGM. Status 4 May 07 We have identified the business for the AGM but have still to agree a venue and date. Status 23 May 07 Notification has been given to shareholders. DacCom Exec members have been reminded of the need to stand for re-election. A request for nominations for additional Exec members has been made at Locality. Agenda papers are being prepared and will be circulated in early June. |
| 013 | MJ | Demonstrate DacCom’s achievement of Level 3 objectives to the PbC Governance Sub-Committee. | 30 Jun 07 | Identified 18 Apr 07 Status 4 May 07 Mark has identified all the necessary inputs and is making good progress. Status 23 May 07 Another draft has been circulated. We are continuing to make progress. |
| 014 | MJ | Coordinate practices’ sign-up to the PbC LES. Send papers to the practice managers by e-mail and ask Michelle to send hard copy to the practices. | 11 May 07 | Identified 18 Apr 07 Status 4 May 07 We have received signed agreements from 5 practices so far. Status 23 May 07 We have agreements from 14 practices. Chris will identify those outstanding on 23 May and Mark will follow up with them. |
| 016 | CW SN | Develop a costed business case for the COPD project and submit this to the PbC Governance Sub-Committee. | 31 May 07 | Identified 18 Apr 07 Status 4 May 07 This is now planned for the June Governance Committee Meeting. See also action 021. |
| 019 | CW | Identify the budgets for Mental Health Services & Counselling and communicate these to Richard Gallow. | 30 Apr 07 | Identified 18 Apr 07 Status 4 May 07 This has been done for counselling. Budgets should also be sent to Dorothy Pluck and Michael Drake. |
| 020 | MJ / SN CW | Facilitate a meeting of those involved in the Counselling project to ensure roles and deliverables are clear. | 11 May 07 | Identified 18 Apr 07 Status 4 May 07 Chris will follow-up messages sent by Mark and ensure the meeting is arranged. Status 23 May 07 A meeting has been arranged for 5 June at Bennetts End. Mark will try to attend to facilitate. |
| 021 | CW | Secure SN’s input to lead the development of an implementation plan for the COPD project. | 11 May 07 | Identified 4 May 07 |
| 022 | CW | Confirm status of funds assigned (or to be assigned) to DacCom at 1 April 07: DES aspiration payment DES achievement payment Balance of DES funding Funding from the LES (assume level 3 for full year) Less invoices paid to Date | 23 May 07 | Identified 4 May 07 Status 23 May 07 a) £35,859 has been paid b)/c) £36,298 is due d) Chris will find out e) Mary has these data already on file |
| 023 | MM | Review income and spend to date against DacCom’s operational budget | Standing agenda item | Identified 4 May 07 Status 23 May 07 DacCom Exec members need to send their April timesheets to MM. The only ones available to date are MJ’s and MM’s. Need to know accurate spends! |
| 026 | MJ | Invite all management leads to attend future programme management meetings | 25 May 07 | Identified 23 May |

Next action 027