Last Meeting:

Thursday 7 June 2007

Attended by:

| Mark Jones | Suzanne Novak | Christine Walden |
| --- | --- | --- |
| Mary McMinn | Sue Rivers-Brown | Colin Neal |

Apologies:

| Sapana Sheth | Dorothy Pluck | Sandy Gower |
| --- | --- | --- |

Next Meeting:

Friday 22 June 2007 @ 11.00 am at Fernville Surgery

Project Milestone Report:

Key Decisions:

- Funding for counselling will be rolled forward until end-January 2007 to allow the team more time to reconfigure the service.

Actions closed in this report:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 011 | MJ | Identify clinical leads and management leads for projects: New Dacorum Hospital - done Enhanced Services - done Community Nursing - done Prescribing – done Referral Management - done Diabetes – done | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 The action has been modified to maintain alignment with the Business Plan. Status 4 May 07 We now have confirmed leads for most items. Mark has asked all GPs for a volunteer to lead for Community Nursing but has had no response. Complete 7 Jun 07 Avi Gupta will lead for Community Nursing |
| 016 | CW SN | Develop a costed business case for the COPD project and submit this to the PbC Governance Sub-Committee. | 31 May 07 | Identified 18 Apr 07 Status 4 May 07 This is now planned for the June Governance Committee Meeting. See also action 021. Closed 7 Jun 07 Replaced by action 031. |
| 019 | CW | Identify the budgets for Mental Health Services & Counselling and communicate these to Richard Gallow. | 30 Apr 07 | Identified 18 Apr 07 Status 4 May 07 This has been done for counselling. Budgets should also be sent to Dorothy Pluck and Michael Drake. Closed 7 Jun 07 Replaced by actions 027-030. |
| 020 | MJ / SN CW | Facilitate a meeting of those involved in the Counselling project to ensure roles and deliverables are clear. | 11 May 07 | Identified 18 Apr 07 Status 4 May 07 Chris will follow-up messages sent by Mark and ensure the meeting is arranged. Status 23 May 07 A meeting has been arranged for 5 June at Bennetts End. Mark will try to attend to facilitate. Complete 7 Jun 07 Actions arising have been added to this list. |
| 021 | CW | Secure SN’s input to lead the development of an implementation plan for the COPD project. | 11 May 07 | Identified 4 May 07 Closed 7 Jun 07 Replaced by action 031. |
| 026 | MJ | Invite all management leads to attend future programme management meetings | 25 May 07 | Identified 23 May Complete 7 Jun 07 |

Ongoing Actions:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 008 | CW | Secure progress of Heart Failure Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 4 May 07 It would be helpful to build confidence in the process to Milestone 2 before putting this project through Milestone 1. So this action will follow action 021. |
| 009 | MJ | Work with Dorothy Pluck to secure progress of Counselling Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. |
| 010 | MJ | Work with Sandy Gower to secure progress of Physiotherapy Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. |
| 012 | MM | Identify actions to deliver the Company AGM. | 31 May 07 | Identified 30 Mar 07 Status 18 Apr 07 Mary has asked Richard Walker for the date of the next Hot Topics Meeting, which could be a vehicle for the AGM. Status 4 May 07 We have identified the business for the AGM but have still to agree a venue and date. Status 23 May 07 Notification has been given to shareholders. DacCom Exec members have been reminded of the need to stand for re-election. A request for nominations for additional Exec members has been made at Locality. Agenda papers are being prepared and will be circulated in early June. Status 7 June Mary will send reminders regarding attendance. Mark will draft a Directors Report. We may defer the appointment of additional Exec members until after the AGM (when we will know for sure how many vacancies exist). New members would be subject to re-appointment by the shareholders at the next AGM. |
| 013 | MJ | Demonstrate DacCom’s achievement of Level 3 objectives to the PbC Governance Sub-Committee. | 30 Jun 07 | Identified 18 Apr 07 Status 4 May 07 Mark has identified all the necessary inputs and is making good progress. Status 23 May 07 Another draft has been circulated. We are continuing to make progress. Status 7 June We expect to submit a progress report at the July meeting. |
| 014 | MJ | Coordinate practices’ sign-up to the PbC LES. Send papers to the practice managers by e-mail and ask Michelle to send hard copy to the practices. | 11 May 07 | Identified 18 Apr 07 Status 4 May 07 We have received signed agreements from 5 practices so far. Status 23 May 07 We have agreements from 14 practices. Chris will identify those outstanding on 23 May and Mark will follow up with them. Status 7 June Chris will identify practices that have not returned the signed agreement with DacCom by 8 June. |
| 022 | CW | Confirm status of funds assigned (or to be assigned) to DacCom at 1 April 07: DES aspiration payment DES achievement payment Balance of DES funding Funding from the LES (assume level 3 for full year) Less invoices paid to Date | 23 May 07 | Identified 4 May 07 Status 23 May 07 a) £35,859 has been paid b)/c) £36,298 is due d) Chris will find out e) Mary has these data already on file Status 7 June d) £415,437 is available to Dacorum, but this includes payments to practices. Suzanne is seeking a breakdown to identify the sum available to DacCom |
| 023 | MM | Review income and spend to date against DacCom’s operational budget | Standing agenda item | Identified 4 May 07 Status 23 May 07 DacCom Exec members need to send their April timesheets to MM. The only ones available to date are MJ’s and MM’s. Need to know accurate spends! Status 7 June This can proceed on completion of action 022. |
| 027 | MJ / SN | Ensure the counselling project team receives clear direction regarding deliverables and constraints of content and budget. | 15 Jun 07 | Identified 7 June 07 Mark will communicate results from our discussion to the team. |
| 028 | SN | Provide the counselling project team with documentation regarding the proposals developed by WatCom | 15 Jun 07 | Identified 7 June 07 |
| 029 | SN | Provide the counselling project team with the report from Joan Foster's review. | 15 Jun 07 | Identified 7 June 07 |
| 030 | MJ / SN | Facilitate a decision regarding roll forward of funding for the existing counselling service. | 15 Jun 07 | Identified 7 Jun 07 We will roll funding forward to end Jan 07. Chris will write to the counsellors and to the practices communicating this decision. |
| 031 | MJ | Set up a meeting involving SN, MJ, Corina Ciobanu, Katrina Power and Jeremy Maynard to ensure everything necessary is in place to progress the COPD project. | 22 Jun 07 | Identified 7 Jun 07 |
| 032 | MJ | Write to the practices explaining the process for initiating a new project (via milestone 1). Write to the NAP and to Everest House regarding their specific proposals. | 22 Jun 07 | Identified 7 Jun 07 |
| 033 | MJ | Provide SRB with a copy of the milestone 1 report for COPD. | 8 Jun 07 | Identified 7 Jun 07 |

Next action 034