Last Meeting:

Wednesday 11 July 2007

Attended by:

| Mark Jones | Christine Walden | Sue Rivers-Brown |
| --- | --- | --- |
| Mary McMinn | Colin Neal |  |

Apologies:

| Sapana Sheth | Dorothy Pluck | Sandy Gower |
| --- | --- | --- |
| Suzanne Novak |  |  |

Next Meeting:

Wednesday 25 July 2007 @ 11.00 am at Fernville Surgery

Key Decisions:

- Sue presented the Milestone 1 Report for the Enhanced Services Project.  We agreed the project has passed this milestone.

- Regarding the preparation of business cases for proposed new LESs, it is important that the project team defines the input needed from the originator (action 037).

- All information required for Milestone 1 was covered in presentations to the Governance Sub-Committee for the Referral Management Project. We agreed the project has passed this milestone subject to Mary’s completion of the report (action 038).

Project Milestone Report:

Actions closed in this report:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 013 | MJ | Demonstrate DacCom’s achievement of Level 3 objectives to the PbC Governance Sub-Committee. | 30 Jun 07 | Identified 18 Apr 07 Status 4 May 07 Mark has identified all the necessary inputs and is making good progress. Status 23 May 07 Another draft has been circulated. We are continuing to make progress. Status 7 June We expect to submit a progress report at the July meeting. Status 22 Jun 07 Mark will revise the draft again and submit it for the July meeting. Completed 2 Jul 07 Mark made a bold and imaginative presentation (!) Funding at level 3 was confirmed. |
| 014 | MJ | Coordinate practices’ sign-up to the PbC LES. Send papers to the practice managers by e-mail and ask Michelle to send hard copy to the practices. | 11 May 07 | Identified 18 Apr 07 Status 4 May 07 We have received signed agreements from 5 practices so far. Status 23 May 07 We have agreements from 14 practices. Chris will identify those outstanding on 23 May and Mark will follow up with them. Status 7 June Chris will identify practices that have not returned the signed agreement with DacCom by 8 June. Status 22 June We have agreements from 17 Practices. The remaining 2 are: Markyate: Mark will meet Dr Sepai on 28 June to discuss it New Surgery: Dr Hall-Jones has made it clear he will not sign Closed 11 Jul 07 Mark met with Dr Sepai and explained his options. The best description of his position would be “has not joined yet but might do so in future.” |
| 034 | MJ | Identify or establish a suitable forum for managing prescribing and referral management actions with the Practices. Attendance should be mandatory (as for other local commissioning organisations). | July 07 | Identified 22 June Completed 2 Jul 07 We have agreed this will be done through the locality meeting / prescribing leads meeting. Mark has sent a letter to practices informing them of the requirement to attend. |
| 035 | MM | Develop a process for managing referral management actions with the Practices. | July 07 | Identified 22 June Closed 11 Jul 07 This is addressed by the approval of the PARS project, which will deliver referral management. The Executive also has plans for individual practice visits. |
| 036 | SS | Develop a process for managing prescribing actions with the Practices. | July 07 | Identified 22 June Closed 11 Jul 07 Richard Gallow will progress this in the Locality Meetings. The Executive also has plans for individual practice visits. |

Ongoing Actions:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 008 | CW | Secure progress of Heart Failure Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 4 May 07 It would be helpful to build confidence in the process to Milestone 2 before putting this project through Milestone 1. So this action will follow action 021. |
| 009 | MJ | Work with Dorothy Pluck to secure progress of Counselling Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. |
| 010 | MJ | Work with Sandy Gower to secure progress of Physiotherapy Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. Status 22 Jun 07 Sandy has had a first meeting with the team and is working on the report for Milestone 1. This should be complete by end-July. Status 11 Jul 07 A project team meeting has been arranged for 19 July. |
| 022 | CW | Confirm status of funds assigned (or to be assigned) to DacCom at 1 April 07: DES aspiration payment DES achievement payment Balance of DES funding Funding from the LES (assume level 3 for full year) Less invoices paid to Date | 23 May 07 | Identified 4 May 07 Status 23 May 07 a) £35,859 has been paid b)/c) £36,298 is due d) Chris will find out e) Mary has these data already on file Status 7 June d) £415,437 is available to Dacorum, but this includes payments to practices. Suzanne is seeking a breakdown to identify the sum available to DacCom. Chris will chase this |
| 023 | MM | Review income and spend to date against DacCom’s operational budget | Standing agenda item | Identified 4 May 07 Status 23 May 07 DacCom Exec members need to send their April timesheets to MM. The only ones available to date are MJ’s and MM’s. Need to know accurate spends! Status 7 June This can proceed on completion of action 022. |
| 037 | SR-B | Ensure the project team defines the input needed from the originator to the preparation of business cases for new LESs | 25 Jul | Identified 11 Jul 07 |
| 038 | MM | Complete the Milestone 1 report for the Referral Management project. | 25 Jul | Identified 11 Jul 07 |
| 039 | SR-B | Provide Mark with electronic copy of the Milestone 1 Report for the Enhanced Services Project. | 25 Jul | Identified 11 Jul 07 |

Next action 040