Last Meeting:

Friday 10 August 2007

Attended by:

| Mark Jones | Christine Walden | Sue Rivers-Brown |
| --- | --- | --- |
| Mary McMinn |  |  |

Apologies:

| Sapana Sheth | Dorothy Pluck | Sandy Gower |
| --- | --- | --- |
| Colin Neal | Suzanne Novak |  |

Next Meeting:

Wednesday 29 August 2007 @ 11.00 am at Fernville Surgery

Key Decisions:

- We need to create a proposal to re-commission, modify or discontinue existing LESs.  A case to continue could be based on assessment of what happens if the service is stopped, and the cost / risk of this.  The proposal will then be presented to the Governance Sub-committee.

Project Milestone Report:

Actions closed in this report:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 022 | CW | Confirm status of funds assigned (or to be assigned) to DacCom at 1 April 07: DES aspiration payment DES achievement payment Balance of DES funding Funding from the LES (assume level 3 for full year) Less invoices paid to Date | 23 May 07 | Identified 4 May 07 Status 23 May 07 a) £35,859 has been paid b)/c) £36,298 is due d) Chris will find out e) Mary has these data already on file Status 7 June d) £415,437 is available to Dacorum, but this includes payments to practices. Suzanne is seeking a breakdown to identify the sum available to DacCom. Chris will chase this Status 25 Jul 07 Funding for 2006/07 through the DES was £71,718 (£ 35,859 aspiration and £35,859 reward) Claims for 2006/07 total £42,895 (now paid) leaving a balance of £28,823 Complete 8 Aug 07 LES funding for DacCom is £188,595 |
| 040 | MJ | Contact Dorothy Pluck to determine whether progress is being made with the counselling project or whether any further action is needed. | 10 Aug | Identified 25 Jul 07 Complete 2 Aug 07 Dorothy expects to submit a Milestone 1 report at the end of August. Thereafter she will have to relinquish her role as project lead. See action 042. |
| 037 | SR-B | Ensure the project team defines the input needed from the originator to the preparation of business cases for new LESs | 25 Jul | Identified 11 Jul 07 Status 25 Jul 07 The process should be: a) Originator submits a Milestone 1 report to this group b) We make a recommendation to the DacCom Exec: endorse or reject the proposal c) The originator then prepares a business case (with PCT support) d) Business case reviewed by the Governance Sub-Committee Closed 10 Aug 07 Instructions detailed above will be given as the need arises. |

Ongoing Actions:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 008 | CW | Secure progress of Heart Failure Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 4 May 07 It would be helpful to build confidence in the process to Milestone 2 before putting this project through Milestone 1. So this action will follow action 021. |
| 009 | MJ | Work with Dorothy Pluck to secure progress of Counselling Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. Status 2 Aug 07 Dorothy expects to submit a Milestone 1 report at the end of August. |
| 010 | MJ | Work with Sandy Gower to secure progress of Physiotherapy Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. Status 22 Jun 07 Sandy has had a first meeting with the team and is working on the report for Milestone 1. This should be complete by end-July. Status 11 Jul 07 A project team meeting has been arranged for 19 July. |
| 023 | MM | Review income and spend to date against DacCom’s operational budget | Standing agenda item | Identified 4 May 07 Status 25 Jul 07 Invoices for first quarter 2007/8 were given to CW on 11 July 2007 – total £20,383 (but no claims were received from DP, SG or ZH) Planned spend for the first quarter was £41,250 |
| 041 | SN | Determine whether it is possible to secure funding for the PARS pilot as a LES. | 10 Aug | Identified 25 Jul 07 Status 10 Aug 07 Suzanne is trying to set up a meeting for this to be discussed w/c 13 August. |
| 042 | MJ | Identify a new management lead for the counselling project. | 31 Aug | Identified 2 Aug 07 |
| 043 | SR-B | Create a proposal to re-commission, modify or discontinue existing LESs. A case to continue could be based on assessment of what happens if the service is stopped, and the cost / risk of this. The proposal will then be presented to the Governance Sub-committee. | 31 Oct | Identified 10 Aug 07 |

Next action 044