Last Meeting:

Wednesday 17 October 2007

Attended by:

| Mark Jones | Mary McMinn | Sue Rivers-Brown |
| --- | --- | --- |
| Geoff Smith | Sandy Gower | Janice Omar |

Apologies:

| Sapana Sheth | Colin Neal | Suzanne Novak |
| --- | --- | --- |
| Tom Kerr |  |  |

Next Meeting:

Thursday 1 November 2007 @ 12 noon at Fernville Surgery

Project Status:

| Project | Clinical Lead | Lead Manager | Status |
| --- | --- | --- | --- |
| New Dacorum Hospital | Richard Walker | Mary McMinn | We are working towards a precise definition of services to be provided. |
| Urgent Care | Meena Savla | Mark Jones | 17 GPs and Managers from 11 Practices attended a key meeting on 2 October at which two potential business partners (Harmoni and Herts Urgent Care) presented their visions for the Urgent Care Centre and Out of Hours Service in Dacorum. We agreed a consensus in favour of forming a Joint Venture with Harmoni to bid as a potential provider for the Urgent Care Centre. We agreed that Meena Savla and Mark Jones should continue as our representatives and begin discussions with Harmoni. These discussions are now underway. |
| Referral Management | Gerry Bulger | Mary McMinn | We have agreed to a ‘fast-track’ tendering process. A service specification and assessment criteria have been drafted. GP engagement has been given the highest priority. DacCom representation on the assessment panel will ensure an appropriate outcome. |
| Enhanced Services | Trevor Fernandes | Sue Rivers-Brown | SRB has prepared a detailed analysis of the case for continuing current LES services. The PBC Governance Sub-Committee has agreed existing services will be rolled out to 31 March 2008. Meanwhile the PCT is assessing inequities across Hertfordshire and will give guidance to inform the 2008/9 programme. It would be prudent to assume a levelling down rather than a levelling up. |
| COPD | Corina Ciobanu | Mark Jones | A detailed Business Plan was presented to the Governance Sub-Committee on 16 October. Further discussions are needed to obtain the buy-in of all interested parties including WatCom, StahCom, PCT Finance, etc |
| Heart Failure | Corina Ciobanu | Chris Walden | Work on a Business Plan will follow COPD. |
| Diabetes | Elizabeth Ponsonby | Tom Kerr | EP has engaged with the initiative to produce a service specification that meets national requirements. Meanwhile, we need to optimise the effectiveness of the retinal screening service locally. With our prompting, appropriate arrangements are to be put in place by the current service provider. |
| Mental Health | Bernie Tipple |  | We have been approached by the current service provider, who wishes to set up a working party to consider service redesign. We will review our position within the Executive before responding. |
| Counselling | Michael Drake | Geoff Smith | Geoff Smith has kindly agreed to take over from Dorothy Pluck as the management lead. There is still some confusion in DacCom about exactly what was intended by the project team. Geoff will assess this and define the issues for decision. |
| Physiotherapy | Avi Gupta | Sandy Gower | The team has made great progress towards a business case but financial information is urgently required from the PCT. Further progress cannot be made until this is addressed. |
| Community Nursing | Avi Gupta | Colin Neal | CN is involved in local meetings regarding the service. He has requested a package of necessary information from Provider Services, which has not yet been forthcoming. |
| Prescribing | Richard Gallow | Sapana Sheth | The programme of Prescribing Leads Meetings is underway, and prescribing issues are addressed in the Practice visits. |

Actions closed in this report:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 042 | MJ | Identify a new management lead for the counselling project. | 31 Aug | Identified 2 Aug 07 Status 12 Sep 07 Request sent to practice managers 17 Aug. Complete 17 Oct 07 Geoff Smith has kindly agreed to help with this. |
| 046 | MJ | Ensure the proposals for a) recommissioning LES services and b) a Retinal Screening LES are submitted to the PBC Governance Sub-Committee on 16 October | Sep 07 | Identified 12 Sep 07 Status 28 Sep 07 Item (b) is no longer required as appropriate arrangements are to be put in place by the service provider. Complete 17 Oct 07 |

Ongoing Actions:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 008 | CW | Secure progress of Heart Failure Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 4 May 07 It would be helpful to build confidence in the process to Milestone 2 before putting this project through Milestone 1. So this action will follow action 021. |
| 009 | MJ | Work with Dorothy Pluck to secure progress of Counselling Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. Status 2 Aug 07 Dorothy expects to submit a Milestone 1 report at the end of August. Status 28 Sep 07 A proposal has been received and will be reviewed at the Executive meeting on 28 September. Status 17 Oct 07 The team still needs to present a financial plan and to define the procurement route. A meeting was held on 12 October to define requirements in detail. See also action 048. |
| 010 | MJ | Work with Sandy Gower to secure progress of Physiotherapy Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. Status 22 Jun 07 Sandy has had a first meeting with the team and is working on the report for Milestone 1. This should be complete by end-July. Status 11 Jul 07 A project team meeting has been arranged for 19 July. Status 17 Oct 07 See action 049. |
| 023 | MM | Review income and spend to date against DacCom’s operational budget | Standing agenda item | Identified 4 May 07 Status 25 Jul 07 Invoices for first quarter 2007/8 were given to CW on 11 July 2007 – total £20,383 (but no claims were received from DP, SG or ZH) Planned spend for the first quarter was £41,250 |
| 045 | CW JO | Facilitate the provision of information regarding Community Nursing requested by CN from Provider Services. | Sep 07 | Identified 12 Sep 07 |
| 047 | TBD | Identify a nurse representative to join the Executive. | Oct 07 | Identified 17 Sep 07 Status 17 Oct 07 Katrina Hall has suggested a structure of locality community nursing leads to work with the PBC groups. If implemented this proposal would address our need. |
| 048 | GS | Define the outstanding issues to be resolved before the new counselling model is implemented. | 1 Nov 07 | Identified 17 Oct 07 |
| 049 | SG / JO | Sandy will define financial data required to progress the physiotherapy project and Janice will obtain this from the PCT. | 1 Nov 07 | Identified 17 Oct 07 |

Next action 050