Last Meeting:

Thursday 1 November 2007

Attended by:

| Mark Jones | Mary McMinn | Janice Omar |
| --- | --- | --- |
| Geoff Smith |  |  |

Apologies:

| Sapana Sheth | Colin Neal | Suzanne Novak |
| --- | --- | --- |
| Tom Kerr | Sue Rivers-Brown | Sandy Gower |

Next Meeting:

Friday 16 November 2007 @ 12 noon at Fernville Surgery

Project Status:

| Project | Clinical Lead | Lead Manager | Status |
| --- | --- | --- | --- |
| New Dacorum Hospital | Richard Walker | Mary McMinn | We are working towards a precise definition of services to be provided. |
| Urgent Care | Meena Savla | Not required | An expression of interest as a potential provider for the Urgent Care Centre has been submitted on behalf of a potential Joint Venture Company, Dacorum Harmoni Healthcare Limited. We now have a great deal of work to do to put in place the business structures necessary to underpin a credible bid. |
| Referral Management | Gerry Bulger | Mary McMinn | Archway elected not to bid for the contract as specified for the tender process. A number of other bids were considered at an assessment panel on 17 October. None met our acceptance criteria. We now have to establish a new plan. |
| Enhanced Services | Trevor Fernandes | Sue Rivers-Brown | SRB has prepared a detailed analysis of the case for continuing current LES services. The PBC Governance Sub-Committee has agreed existing services will be rolled out to 31 March 2008. Meanwhile the PCT is assessing inequities across Hertfordshire and will give guidance to inform the 2008/9 programme. It would be prudent to assume a levelling down rather than a levelling up. |
| COPD | Corina Ciobanu | Mark Jones | A detailed Business Plan was presented to the Governance Sub-Committee on 16 October. Further discussions are needed to obtain the buy-in of all interested parties including WatCom, StahCom, PCT Finance, etc |
| Heart Failure | Corina Ciobanu | Chris Walden | Work on a Business Plan will follow COPD. |
| Diabetes | Elizabeth Ponsonby | Tom Kerr | EP has engaged with the initiative to produce a service specification that meets national requirements. Meanwhile, we need to optimise the effectiveness of the retinal screening service locally. With our prompting, appropriate arrangements are to be put in place by the current service provider. |
| Mental Health | Bernie Tipple |  | We have been approached by the current service provider, who wishes to set up a working party to consider service redesign. We will review our position within the Executive before responding. |
| Counselling | Michael Drake | Geoff Smith | Geoff has identified outstanding questions for resolution. A meeting with Michael Drake ahs been arranged for 14 November, following which a firm proposal will be documented. |
| Physiotherapy | Avi Gupta | Sandy Gower | The team has made great progress towards a business case but financial information is urgently required from the PCT. Further progress cannot be made until this is addressed. |
| Community Nursing | Avi Gupta | Colin Neal | CN is involved in local meetings regarding the service. He has requested a package of necessary information from Provider Services, which has not yet been forthcoming. |
| Prescribing | Richard Gallow | Sapana Sheth | The programme of Prescribing Leads Meetings is underway, and prescribing issues are addressed in the Practice visits. |

Programme Management Budget Status:

| Period | Budget period | Spend period | Variance | Budget to date | Spend to date | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| 1Q 07/8 | £47,148 | £20,383 | £26,765 | £47,148 | £20,383 | £26,765 |
| 2Q 07/8 | £47,148 | £26,160 | £20,989 | £94,296 | £46,583 | £47,713 |

Actions closed in this report:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 023 | MM | Review income and spend to date against DacCom’s operational budget | Standing agenda item | Identified 4 May 07 Status 25 Jul 07 Invoices for first quarter 2007/8 were given to CW on 11 July 2007 – total £20,383 (but no claims were received from DP, SG or ZH) Planned spend for the first quarter was £41,250 Closed 1 Nov 07 This item has been added to the status report |
| 048 | GS | Define the outstanding issues to be resolved before the new counselling model is implemented. | 1 Nov 07 | Identified 17 Oct 07 Complete 1 Nov 07 A meeting with Michael Drake has been arranged for 14 November, following which a firm proposal will be documented. |
| 050 | MJ | Determine whether counselling budgets can be rolled forward to 31 Mar 07 at current rates | 2 Nov 07 | Identified 1 Nov 07 Complete 1 Nov 07 This was agreed at the Executive Meeting on 1 Nov 07. This decision is consistent with our actions for LES services. |

Ongoing Actions:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 008 | CW | Secure progress of Heart Failure Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 4 May 07 It would be helpful to build confidence in the process to Milestone 2 before putting this project through Milestone 1. So this action will follow action 021. |
| 009 | MJ | Work with Dorothy Pluck to secure progress of Counselling Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. Status 2 Aug 07 Dorothy expects to submit a Milestone 1 report at the end of August. Status 28 Sep 07 A proposal has been received and will be reviewed at the Executive meeting on 28 September. Status 17 Oct 07 The team still needs to present a financial plan and to define the procurement route. A meeting was held on 12 October to define requirements in detail. See also action 048. |
| 010 | MJ | Work with Sandy Gower to secure progress of Physiotherapy Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. Status 22 Jun 07 Sandy has had a first meeting with the team and is working on the report for Milestone 1. This should be complete by end-July. Status 11 Jul 07 A project team meeting has been arranged for 19 July. Status 17 Oct 07 See action 049. |
| 045 | CW JO | Facilitate the provision of information regarding Community Nursing requested by CN from Provider Services. | Sep 07 | Identified 12 Sep 07 |
| 047 | TBD | Identify a nurse representative to join the Executive. | Oct 07 | Identified 17 Sep 07 Status 17 Oct 07 Katrina Hall has suggested a structure of locality community nursing leads to work with the PBC groups. If implemented this proposal would address our need. |
| 049 | SG / JO | Sandy will define financial data required to progress the physiotherapy project and Janice will obtain this from the PCT. | 1 Nov 07 | Identified 17 Oct 07 |

Next action 051