Last Meeting:

Thursday 20 December 2007

Attended by:

| Mark Jones | Mary McMinn | Geoff Smith |
| --- | --- | --- |

Apologies:

| Sue Rivers-Brown | Colin Neal | Suzanne Novak |
| --- | --- | --- |
| Tom Kerr | Sandy Gower |  |

Next Meeting:

Wednesday 30 January 2008 @ 12 noon at Fernville Surgery

Project Status:

| Project | Clinical Lead | Lead Manager | Status |
| --- | --- | --- | --- |
| New Dacorum Hospital | Richard Walker | Mary McMinn | Discussions continue as part of the Acute Services Review. Negotiations between the PCT and the Urgent Care Centre provider will have a significant influence on the services to be retained on the Hemel Hospital site. |
| Urgent Care | We may need to reappoint leads now the contracting process is underway. This will exclude anyone with an interest in a potential provider. | The PCT has received Pre-Qualification Questionnaires from potential providers. DacCom is not able to comment on the progress of individual bids, including any bid(s) in which Dacorum Practices may be involved. |
| Referral Management | Gerry Bulger | Mary McMinn | We will put in place a manageable programme of targeted data validation. To support this, HIDAS training and budget training has been arranged for Practice Managers. |
| Enhanced Services | Trevor Fernandes | Sue Rivers-Brown | SRB has prepared a detailed analysis of the case for continuing current LES services. The PBC Governance Sub-Committee has agreed existing services will be rolled out to 31 March 2008. Meanwhile the PCT is assessing inequities across Hertfordshire and will give guidance to inform the 2008/9 programme. We need to ensure this input is received promptly, so that we can proceed with the definition of services to be commissioned next year. |
| COPD | Corina Ciobanu | Mark Jones | Meetings have been arranged with WatCom and StahCom to progress the joint commissioning of the new service. PCT Finance have assessed our financial plan, and have drawn similar conclusions to ours regarding risks and mitigation. We may need further discussion to address fully all concerns. |
| Heart Failure | Corina Ciobanu | Chris Walden | Work on a Business Plan will follow COPD. |
| Diabetes | Elizabeth Ponsonby | Tom Kerr + Sue Rivers- Brown (retinal screening) | The new retinal screening service is now close to launch. We are still arguing for an accessible site in Hemel instead of the proposed location at Grovehill. Clinical leads from the West Herts PBC groups have completed the redesign of diabetic care pathways. This would transfer much of the service to primary care along with appropriate clinical resources and funding. |
| Mental Health | Bernie Tipple |  | A meeting has been held to discuss proposals from HPFT in detail. There is much of value in these proposals, but more work to be done before a redesigned service can be agreed. |
| Counselling | Michael Drake | Geoff Smith | We intend to submit a proposal for a Counselling LES to the January meeting of the PBC Governance Sub-Committee. |
| Physiotherapy | Avi Gupta | Sandy Gower | A proposal for a more equitable and rationalised service has been drafted. But financial information is urgently required from the PCT. Further progress cannot be made until this is addressed. |
| Intermediate Care | Avi Gupta | Colin Neal | CN is involved in local meetings regarding the service. He has requested a package of necessary information from Provider Services, which has not yet been forthcoming. |
| Prescribing | Richard Gallow |  | Regular meetings are held (quarterly) with a Local Pharmacist Lead. To ensure actions are communicated effectively; these meetings are followed within 4 weeks by meetings of Practice GP Leads. DacCom has taken action to control huge overspends occurring in the recent past and is currently within budget for prescribing overall. DacCom compares favourably with other localities for most EoE metrics. We would be close to achieving almost all targets but for one large practice, which is overspending by a substantial amount. This must be addressed, as the situation is are not improving. Advice is being sought. Current projects include action to reverse the increasing trend in prescribing of food supplements; and regular "Good Buy" bulletins sent to all GPs to communicate changes in prescribing costs and draw attention to products, which have become good buys (eg coming off patent). |
| Maternity Services | Zunia Hurst |  | We have raised our concerns regarding the PCT’s proposed service redesign with the West Herts PBC Leads, who share our view. PCT personnel will be invited to the Leads Meeting in January to discuss the issue. |

Programme Management Budget Status:

| Period | Budget period | Spend period | Variance | Budget to date | Spend to date | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| 1Q 07/8 | £47,148 | £20,383 | £26,765 | £47,148 | £20,383 | £26,765 |
| 2Q 07/8 | £47,148 | £26,160 | £20,989 | £94,296 | £46,583 | £47,713 |
| 3Q 07/08 | £47,148 | £34,250 | £12,898 | £141,444 | £80,793 | £60,651 |

Actions closed in this report:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |

Ongoing Actions:

| ID | Who | Does what | By when | Status |
| --- | --- | --- | --- | --- |
| 008 | CW | Secure progress of Heart Failure Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 4 May 07 It would be helpful to build confidence in the process to Milestone 2 before putting this project through Milestone 1. So this action will follow action 021. |
| 010 | MJ | Work with Sandy Gower to secure progress of Physiotherapy Project through Milestone 1. | 30 Apr 07 | Identified 30 Mar 07 Status 18 Apr 07 Mark will provide the Milestone 1 report for the COPD project as a model. Status 22 Jun 07 Sandy has had a first meeting with the team and is working on the report for Milestone 1. This should be complete by end-July. Status 11 Jul 07 A project team meeting has been arranged for 19 July. Status 17 Oct 07 See action 049. Status 20 Oct 07 A proposal for a more equitable and rationalised service has been drafted. |
| 045 | CW JO | Facilitate the provision of information regarding Community Nursing requested by CN from Provider Services. | Sep 07 | Identified 12 Sep 07 Status 16 Nov 07 A meeting has been arranged |
| 049 | SG / JO | Sandy will define financial data required to progress the physiotherapy project and Janice will obtain this from the PCT. | 1 Nov 07 | Identified 17 Oct 07 |
| 051 | JO | Implement the extension of counselling funding to 31 Mar 08. | 30 Nov 07 | Identified 1 Nov 07 |
| 052 | SRB | Contact SN to check progress with the PCTs assessment of inequalities of LES services across Herts. Determine how this is likely to constrain our definition of services to be commissioned next year. | 5 Dec | Identified 16 Nov 07 |

Next action 053