###### Mark Jones

20 April 2007

Summary

| Level | Achieved? | Areas with 2 targets met & remainder planned | Targets addressed (“Done”) | Targets with plans in place (“Plan”) | Targets with identified action (“In hand”) | Targets with action yet to be identified (highlighted) |
| --- | --- | --- | --- | --- | --- | --- |
| Level 1 | Not yet | 4 of 6 | 9 | 3 | 2 | 0 |
| Level 2 | Not yet | 2 of 6 | 11 | 0 | 2 | 6 |
| Level 3 | Not yet | 0 of 6 | 8 | 6 | 2 | 7 |

Level 1:

| Objective | Target | Status | Action or Evidence |
| --- | --- | --- | --- |
| Good governance of PBC | 75%+ practices signed up to a PBC DES / LES. | Plan | All 19 practices have been invited to sign up to the LES. |
|  | Agreed leadership arrangement for Chair of PBC group. | Done | Mark Jones is the Chair. |
|  | Regular meetings of PBC group PBC group forum. | Done | Meetings have taken place regularly since March 06. Records are on file. |
| Providing high quality and accessible primary care services | Latest QOF scores of 850+ for 75% of the practices in the PBC group | Done | All 19 practices achieved scores >850 in 2005/6. |
|  | 80%+ practices providing Access DES | Done | All 19 practices signed up to the DES. |
| High quality, cost effective prescribing | All practices have agreed prescribing plan with PCT | Done | All practices had a prescribing visit from the PCT in 2006/7. Plans were documented. Some of these were not signed off, and we will address this through our programme management model in 2007/8. |
|  | All practices making progress on EoE prescribing indicators | In hand | Sapana Sheth will provide the information. |
|  | 70%+ practices are making measurable progress against other indicators in plan | In hand | Sapana Sheth will provide the information. |
|  | GP medicines management lead attending area prescribing committee | Done | Zunia Hurst attends meetings of the West Herts Medicines Management Committee |
| Referring on to other services appropriately and active secondary care demand management | Referral information being discussed by the PBC group with named information shared | Done | Referral information has been shared throughout 2006/7 and practices have communicated their plans to manage referrals. We are implementing a more formal system in 2007/8. (Referral Management Lead – Gerry Bulger) |
| Effective collaboration with partner agencies and patients | A Non Exec Director or patient representative and nursing representation invited to PBC group meetings as full members | Plan | A patient representative is invited to all meetings. We need to invite a nursing representative. |
| Demonstration of responsibility and accountability | Clearly identified leadership from GP(s) | Done | GP leads are identified in the Business Plan for 2007/8 and in the monthly Programme Management Status Reports. |
|  | PBC group receives monthly finance/activity performance and impact assessment reports | Plan | This is the PCT’s responsibility. We have identified Mary McMinn as the lead for analysis of financial and activity data in the Business Plan for 2007/8. |
|  | 25% of membership asked to report at every meeting the action they are taking to achieve the agreed PBC plans (e.g. on prescribing) | Done | Meeting agendas are circulated in advance. These include project progress reports. We also track actions systematically in our Programme Management Team. |

Level 2:

| Objective | Target | Status | Action or Evidence |
| --- | --- | --- | --- |
| Good governance of PBC | Lead GPs / others taking responsibility for key areas. | Done | Leads are identified in the Business Plan for 2007/8 and in the monthly Programme Management Status Reports. |
|  | Agreed action plan shared at PBC group and individual practice level | Done | The business plan is shared with all practices, as are the Programme Management Status Reports. |
|  | PBC group forum has involvement of at least 60% of the practices in the geographical area | Done | 9/19 practices are represented on the Executive. Others are involved through the Locality Forum and through Hot Topics Meetings. |
| Providing high quality and accessible primary care services | Latest QOF scores of 900+ for 80% of the practices in the PBC group | Done | 18/19 practices achieved scores >900 in 2005/6. |
|  | 85%+ practices providing Access DES | Done | All 19 practices signed up to the DES. |
|  | GPs actively involved in shaping collective urgent care services to provide accessible urgent primary care | Done | Accessible urgent primary care is a deliverable in the Business Plan for 2007/8 (Lead - Meena Savla) |
| High quality, cost effective prescribing | 80% practices meeting EoE prescribing indicators. | In hand | Sapana Sheth will provide the information. |
|  | 100% making progress on PCT prescribing indictors. | In hand | Sapana Sheth will provide the information. |
|  | PCT Pharmacist represented on the PBC locality group. | Done | Richard Jones, Locality Medicines Management Lead has been co-opted to the Executive. |
|  | Identified GP medicines management lead chairing PBC medicines management committee (plus attending area medicines management subcommittee). |  | Richard Gallow – please advise |
| Referring on to other services appropriately and active secondary care demand management | 80%+ individual practices reporting action being taken to manage demand for secondary care including collective action. |  | Richard Walker – how many practices reported action plans when asked to do so a while ago? |
|  | Evidence of secondary care demand being successfully managed by 50%+ practices through individual or collective action |  | Mary – Can we find evidence in the data we have? |
|  | Evidence that practices have ceased to refer patients for exceptional treatment except where meeting the criteria outlined in the priority forum guidance. |  | How can we address this? |
| Effective collaboration with partner agencies and patients | PBC group meetings also include PCT senior management. | Done | We already include the Assistant Director and there is no objection to any PCT senior manager attending. |
|  | Mechanism in place (such as a subcommittee and agreed GP lead) to undertake joint work with HCC adult care services or Children, School and Families services and another partner agency e.g. hospital, mental health trust or voluntary sector) |  | How should we address this? |
|  | Identified lead to take forward work on patient involvement in PBC | Done | Mary McMinn is working with Heather Aylward on the proposed PBC Network. |
| Demonstration of responsibility and accountability | Identified leads report progress to the PBC group every month against their objectives. | Done | This is done through our Programme Management Structure. A detailed status report is produced at least monthly and circulated to all members of the group. |
|  | Sub committee in place to oversee prescribing plans involving representatives from at least 75% of the practices. |  | Richard Gallow – please advise how we should proceed |
|  | PBC group, through the Chair and with management support from the PCT, reporting progress to the PCT against objectives. | Done | Suzanne Novak is a member of the Programme Management Team which generates detailed status reports at least monthly. |

Level 3:

| Objective | Target | Status | Action or Evidence |
| --- | --- | --- | --- |
| Good governance of PBC | Formal agreements between 90%+ practices in the PBC group in terms of progressing agreed action. | Plan | An agreement has been circulated to all practices for signature. |
|  | Formal agreement between PBC group and PCT. |  | We need to put a formal agreement in place. |
|  | Elected Executive actively managing PBC and held to account by the wider membership. | Done | Election and formal accountability is through the Company AGM. |
| Providing high quality and accessible primary care services | Latest QOF scores 900+ for 90% of the practices in the PBC group. | Done | 18/19 practices achieved scores >900 in 2005/6. |
|  | 90%+ practices providing Access DES. | Done | All 19 practices signed up to the DES. |
|  | Plans in place to develop more accessible urgent primary care services across the PBC group. | Done | A detailed proposal for an urgent care service was developed by DacCom in 2006. These ideas are being progressed within a West Herts-wide project (Dacorum lead – Meena Savla) |
|  | Evidence of joint working with community pharmacists to develop enhanced services e.g. minor ailments. |  | How should we address this? |
| High quality, cost effective prescribing | 90%+ practices meeting EoE prescribing indicators. | In hand | Sapana Sheth will provide the information. |
|  | 80% meeting PCT prescribing indicators. | In hand | Sapana Sheth will provide the information. |
|  | PCT pharmacist an honorary or full member of the PBC Executive. | Done | Richard Jones, Locality Medicines Management Lead has been co-opted to the Executive. |
|  | Identified GP lead on medicines management attending secondary care D&T committees. |  | Richard Gallow – please advise |
|  | PBC Prescribing sub committee to include LPC rep. |  | Richard Gallow – please advise how we should proceed |
| Referring on to other services appropriately and active secondary care demand management | Collective action being taken by practices to better manage secondary care demand. | Plan | A rigorous referral management system for Dacorum has been proposed and a pilot study is underway (Lead – Gerry Bulger). |
|  | Systems in place to routinely scrutinise referral levels by individual practice with agreed action plans. | Plan | This would be achieved by our planned referral management system. |
|  | Evidence of demand being successfully managed by 75%+ practices through individual or collective action. | Plan | This would be achieved by our planned referral management system. |
|  | Evidence that patients are managed through agreed care pathway approach (or something along those lines). | Plan | Care pathways are being developed (first priorities: COPD, Heart Failure, Diabetes). The first of these projects has passed Milestone 1 in our Programme Management process. |
| Effective collaboration with partner agencies and patients | PBC Executive includes a senior manager seconded from the PCT, a nurse/AHP and a lay/patient rep | Plan | Suzanne Novak represents the PCT. Caroline Johnson represents PPI We need to invite a nursing representative. |
|  | A patients’ forum has been identified to link into the PBC and regular meetings scheduled which include GP lead or PBC Chair. | Done | A GP lead attends meetings of the local patients’ forum and they are invited to send a representative to our meetings. |
|  | Sub committees in place with objectives which have been agreed with representatives from at least two partner agencies and the local PBC patients’ forum. |  | How should we address this? |
|  | Regular meetings scheduled between GP leading on medicines management, PBC Chair and LPC rep. | Done | This will be achieved through the participation of these people in the Executive. |
|  | Regular meetings scheduled between PBC commissioners, lead pharmacist for pharmacy contractor development and LPC representative |  | How should we address this? |
| Demonstration of responsibility and accountability | PBC Chair, with senior management support, meets regularly with the Chair of the PBC governance committee to report progress along with other PBC Chairs of localities at level 3 and attends the PBC governance committee when presenting business cases setting out proposed changes. | Done | Mark Jones attends meetings of the governance committee and will present reports and business cases as required. |
|  | PBC group have clear agreed processes to ensure effective collective action is taken if PBC plans drift from targets. |  | How should we address this? |