PBC Business Case

WatCom Primary Care Ophthalmology Clinical Assessment & Treatment Service

Purpose of this paper:

To secure support of WatCom and the PCT PBC Governance Committee to the vision set out in this business case for a primary care ophthalmology clinical assessment and treatment service.

- Background

The Acute Service Review anticipates a shift of at least 40% of ophthalmology Outpatients from secondary to primary care by 2012/13.

The Hertfordshire-wide CATS Review challenges PBC groups to commission Clinical Assessment and Treatment Services (CATS) in order to improve patient care through faster care pathways provided more locally delivered by a multidisciplinary team approach including consultant specialists.

Clinical discussions locally across primary and secondary care have found support in developing new care pathways to stream line the journey for patients and to help implement the ASR.

The Department of Health’s guidance on PBC sets out a vision for “any willing providers” to offer services to appropriate standards to local patients and the GPs managing their care so that choice is maximised and quality of care improved as a result.

- Service to be provided

WatCom would like to commission a Clinical Assessment and Treatment Service for ophthalmology as a prerequisite to referral to secondary care which would improve clinical effectiveness and manage demand by establishing a new care pathways as shown in appendix one.

The service would comprise of:

- Consultant triaging referrals to ophthalmology and directing on to the appropriate service or back to the GP

- Fast track for suspected cancers not sent via the 2 week wait referral process.

- Multi disciplinary team approach including Consultant, GPwSI, specialist nurses and optometrist

- Provision of assessment and treatment where appropriate

- Direct access to diagnostics as appropriate

- Include arrangements for the independent provision of Choice of Secondary Care provider

WatCom are aware of at least one provider interested in providing this service locally within Watford.

.

3.	Benefits for patients

- Faster access

- Provision as local as possible

- Seen by the most appropriate clinician

- Safe service – multi disciplinary approach with consultant expertise

4.	Expected improvements in efficiency and effectiveness

- It is expected that the service would be provided at 20% below the national tariff thus making a saving to the PBC group and PCT

- At least 70% of referrals could be managed without referral to secondary care.

- Follow up rates would be included in the cost per case and capped at a level below the cap currently in place in the SLAs with secondary care providers.

- Help to achieve 18 total waiting times

- Better provision of information on referrals – to support ongoing demand management

- Service expected to monitor referrals and to use this information to identify training/support needs for local GPs in order to continually develop primary care services and skills for improved efficiency

- Providers would be encouraged to establish GP clinical leadership within the service to promote communication with GPs and partnership in managing patients with maximum efficiency and to best effect

5.	Management resources required

It will be for providers to set out what management resource they require to deliver this new service.

In terms of commissioning responsibilities, there will be a lead commissioning manager identified to take forward the procurement process and co-ordinate the assessment of proposals etc.

6.	Costs of the proposals and their recovery period

The negotiating parameters for the commissioning team procuring this service will be that the service must generate savings of at least 15-20% compared to an appropriate period last year and that any investment should be recovered through savings within a period of 12-18 months from establishment.

HIDAS figures show that during 2006/07 ophthalmology out patient activity for WatCom was as follows:

New out patients – 6062

Follow up out patients –11791

For the financial year 2007/08 the costs are as follows:

New ophthalmology out patients PbR tariff: £103   (adult)

Follow up out patients PbR tariff: £49    (adult)

The ophthalmology CATS contract for STAHCom and Hertsmere LMG represents a saving of 20% against the national tariff and this contract is being changed with The Practice to a cost per case basis at £75.00 new and £40.00 follow up with effect from 1 April 2008. Follows ups will be maintained at a ratio of no more than 1:1.64 and steps will be taken to reduce this.

Using The Practice’s figures as an average for the cost of an “Any Willing Provider” service, the savings made would be approximately £183,616.  This is based on the activity quoted above.  See Appendix 2 attached.

As the WatCom contract would be provided under the “Any Willing Provider” approach the negotiating team would be expected to negotiate contracts with all willing providers which are at least as competitive as the Ophthalmology CATS contract currently operating in the east of West Herts.

If no sufficiently competitive proposals are put forward then no new contracts will be agreed.

7.  Action plan for commissioning the service and procurement process as appropriate

It is proposed that this service is commissioned through the “any willing provider” route.  The proposed action plan is:

| Action | By Whom | Timeframe |
| --- | --- | --- |
| Produce draft service specification, business case and PQQ | SBJ/CW | 22 February 2008 |
| WatCom Exec Group approval of service specification and business case | SBJ/CW | 13 March 2008 |
| Present to WatCom Implementation Group for approval | SBJ/CW | 27 March 2008 |
| Secure PCT internal agreement (finance/commissioning/public health) | CW | Up to 11 April 2008 |
| PBC Governance approval | SN/SBJ/CW | 29 April 2008 |
| Issue ‘Intention to Commission’ Notice on PCT website and send to local providers | CW | 12 May 2008 |
| Notify Clive Appleby and arrange for two directors to be present at opening of bids | CW | 12 May – 16 May 2008 |
| Send completed Submission of Tenders document to John Paton | CW | 27 June 2008 |
| Deadline for submission of completed PQQs |  | 30 June 2008 |
| Set up assessment panels and produce panel scoring criteria document | CW | May 2008 |
| Photocopy and send out bids to panel | CW | 1 July 2008 |
| Proposals considered and suitable providers shortlisted by paper assessment | Panel | 7 -11 July 2008 |
| Shortlisted applicants notified of date of presentation panel | CW | 14 July 2008 |
| Presentation by shortlisted applicants | Panel | 21 – 25 July 2008 |
| Contact all applicants with decision and write and confirm details | CW | 25/28 July 2008 |
| Prepare AWP contract | CW | August 2008 |
| Negotiate and sign contracts with providers | CW/SN/AP | August 2008 |
| Services established | Providers | 1 September 2008 |

SBJ – Sheila Borkett-Jones

SN – Suzanne Novak

AP – Alan Pond

CW – Christine Walden

| Criteria | How met |
| --- | --- |
| Evidence based clinical effectiveness and priorities as set by PEC | Shift of secondary to primary care services part of the Acute Services Review. |
| Clinical safety, quality and governance | Consultant/GP led service. Monthly review meetings will be held with providers to ensure service meets the requirements set out in the specification. |
| A contribution to offering care closer to home and delivery of the national 18 weeks priority | Locations of clinics will be in local GP practices and will contribute to the achievement of the 18 week wait. |
| Whether the specific needs of population groups such as disabled people, Black Minority Ethnic communities and the differing needs of men and women/diverse age groups/differing faiths/sexual orientation and groups accessing services has been taken into account | Access to the service will via GP referral and will be open to all population groups. |
| Patient and stake holder support | This service has been agreed at the WatCom Implementation group where there are representatives from each practice and also a PPI representative regularly attends and supports this initiative. |
| Justification/evidence that resources can be released through the substitution of care | This service will be commissioned at 15-20% below national tariff. A similar successful service is operating in the St Albans/Harpenden & Hertsmere PBC groups. |
| Affordability within the current and projected indicative budgets | The service will be affordable as included within the WatCom budget for 08/09 and will be at a lower cost than currently provided. |
| Consideration of whether formal tendering is required to demonstrate value for money or for reasons of probity | Not required as any willing provider route. |
| Assessment of the risks of the development, including the impact on secondary care and financial/activity modelling showing the financial impact on the PCT and relevant secondary care providers | Demand management will be met by central triage of referrals which will signpost referrals to the appropriate service. Impact on secondary care will be monitored to ensure necessary savings are made. |
| The procurement route | Any willing provider as per the paper agreed by the PBC Governance Committee |
| Value for money, including using benchmarked costs to determine a reasonable price range for service. | The cost of the service will be 15-20% below national tariff thereby offering value for money. |

Sheila Borkett-Jones, WatCom Executive GP Member

Christine Walden, PBC Support Manager, WatCom

February 2008

APPENDIX 1

| WatCom Ophthalmology Savings Projection |  |  | APPENDIX 2 |  |  |
| --- | --- | --- | --- | --- | --- |
| Secondary Care 06/07 Referral Activity level |  |  |  |  |  |
|  | Referral 06/07 |  | Upper Quartile |  |  |  |  |
| New Patient | 6062 |  |  |  |  |  |  |
| Follow-Up | 11791 |  |  |  |  |  |  |
| Total | 17853 |  |  |  |  |  |  |
| Follow-up ratio | 1.95 |  | 1.64 |  |  |  |  |
| CATS Activity Projections |  |  |  |  |  |  |  |
| Referral to CATS | 70% |  | Assumed CATS follow-up ratio | 1.50 |  |
| Inappropriate referrals | 2.50% |  |  |  |  |  |  |
| Retention in CATS | 80% |  |  |  |  |  |  |
|  | Total | CATS | Secondary | Inappropriate referral |  |  |  |
| Referrals | 6062 | 3395 | 2561 | 106 |  |  |  |
| Follow-Up | 9293 | 5093 | 4200 |  |  |  |  |
| Follow-up ratio |  | 1.50 | 1.64 |  |  |  |  |
| CATS estimated Cost per Case (based on Practice Networks) |  |  |  |
| First appointment | £75 |  |  |  |  |  |  |
| Follow-Up appointment | £40 |  |  |  |  |  |  |
| COST ANALYSIS |  |  |  |  |  |  |  |
| Secondary Care 06/07 Projected Costs without CATS (with Upper Quartile follow-up ratio) |  |
|  | Referral 06/07 | 07/08 PbR tariff | 07/08 PbR Cost |  |  |  |  |
| New Patient | 6062 | £103 | £624,386 |  |  |  |  |
| Follow-Up | 9942 | £49 | £487,158 |  |  |  |  |
| Total Cost | 16004 | £69.45 | £1,111,544 |  |  |  |  |
| CATS Service Projected Costs incl. Secondary Care referrals |  |  |  |
| CATS First appointments | 3395 | £75 | £254,625 |  |  |  |  |
| CATS Follow-Up appointments | 5093 | £40 | £203,720 |  |  |  |  |
| 2º New Patient | 2561 | £103 | £263,783 |  | (1) |  |  |
| 2º Follow-Up | 4200 | £49 | £205,800 |  | (2) |  |  |
| Total Cost | 15249 | £60.85 | £927,928 |  |  |  |  |
| PROJECTED NET SAVINGS / (NET COSTS) | £183,616 | 16.52% |  |  |  |
| PROJECTED SECONDARY CARE REDIRECTION ACTIVITY AND COSTS |  |  |  |
| CATS First appt. activity | 3395 | £103 | £349,685 |  |  |  |  |
| Inappropriate referrals level | 106 | £103 | £10,918 |  |  |  |  |
|  | 3501 |  | £360,603 |  | (1) |  |  |
| Follow-Up activity level | 5742 | £49 | £281,358 |  | (2) |  |  |
| Total | 9243 |  | £641,961 |  |  |  |  |
| Reconciliation to Total Secondary Care projection: |  |  |  |  |  |
| First appointments | 6062 |  |  |  | (1)s |  |  |
| Follow-Up appointments | 9942 |  |  |  | (2)s |  |  |