COMMISSIONING IN 2008-2009-THE BUSINESS CALENDAR

Presenter at Board meeting:	Peter Jones

Purpose of Paper: To brief the board on the commissioning process timetable for 2008-2009

Assurance Framework Objective:

4 Effective commissioning -Become effective commissioners; develop a performance culture with Smart productivity metrics and deliver the six must do targets

Action Required by Board:

## Key areas for discussion or noting:

- The paper outlines the commissioning process timetable for 2008-09 and encloses the business calendar from which it is derived and

- Notes the major elements which contribute to the formulation of the advance warning of commissioning intentions which will be sent to providers

- Key factors influencing activity changes are highlighted

Peter Jones

Interim Director of Commissioning

19 November 2007

East and North Hertfordshire Primary Care Trust

West Hertfordshire Primary Care Trust

COMMISSIONING IN 2008-2009-THE BUSINESS CALENDAR

# Introduction

Late autumn sees the beginning of planning for commissioning of care services. Before agreements can be finalised the PCT must take into account the complex interplay of national guidance; joint commissioning initiatives and the strategic imperative to move specification of services to primary care.

In order to ensure that the major elements contributing to service provision are taken into account the Executive has drafted a business calendar that itemises steps to be taken by calendar month. It is a work in progress but is guiding the commissioning process. An outline example is attached at enclosure 1.

# Commissioning Intentions

Commissioning intentions are to be issued in December of the year before they commence. They are a simple statement, without detail, and are intended to provide advance warning of any changes of requirements. They derived from key elements which include, amongst others:

- Month 6 figures upon which to base out turn predictions

- Annual Health Check findings

- Draft of National operating frameworks (including targets) and contract templates (Department of Health briefings)

- Public health Needs assessment

- Practice based groups intentions

- PCT local priorities

- Choice

# Commissioned Activity-forecasting the figures

It is not possible to accurately forecast activity figures before the end of January. These will be based upon the out turn but will be adjusted for the effects of various factors (some of which are illustrated in Enclosure 2) which include:

- PBC Service changes agreed by the governance committee ( the approval process is attached at Enclosure 3)

- Implementation of the Acute Services review-first year including the procurement of intermediate care; the commissioning of the urgent care centres and other service changes with impacts on existing agreements

- Activity arising from national initiatives including 18 weeks access policy, Maternity matters and paediatric A&E provision

- Review of services arising from performance and/or capacity issues highlighted by improved access requirements

- Unbundling of block contracts particularly in diagnostics and walk in centres hosted by other PCTs where underlying activity is known to be higher than the existing block indicative figures.

# Immediate Next Steps

The PCT will, by the end of November 2007:

- Brief the PBC groups on the national and local framework

- Submit end of year activity predictions to the SHA

- Finalise the population activity model reflecting gross activity variations s arising from known service and contracting changes

# Recommendations

The Board is requested to:

- Note commissioning process timetable and the business calendar it is derived from.

- Receive a report on commissioning progress in January 2008

Enclosure 1 Enclosure 1 to Commissioning in 2008-2009-the Business Calendar

# October

| What | When | Lead |
| --- | --- | --- |
| Provisional Allocations from NHS |  | DoF |
| Month 4 PBC Activity report |  | DDoC |
| Month 4 finalisation of costs |  | DoF |
| Production of Business activity Calendar |  | DoC |
| What | When | Lead |
| National Operating Framework Brief | 5th | DoF/DoC |
| End of year forecast | 21st | DoF |
| Public Health Needs identification | 21st | DPH |
| PBC framework | 23rd | DPC |
| PBC/PEC PCT operating framework-Briefings commence | 29th | DoC |
| ASR implementation impacts | 30th | DoS |
| Initial forecast of activity to SHA | 30th | DoC |

# November

# December

| What | When | Lead |
| --- | --- | --- |
| Operating Framework; National Contract template; NpFit objectives | 10th | DoF/DoC/DoS |
| SHA Operating Framework | 15th | SHA |
| Draft of PCT Objectives | 22nd | DPPI&CS |
| Service Change proposals-PBC | 31st | DPC |
| Letter of intent to providers | 31st | DoC |
| Draft of LDP | 31st | DoC |
| Decisions on Service change Consultation | 31st | DoS |
| Second cut of activity figures to SHA | 31st | DoC |

# January

| What | When | Lead |
| --- | --- | --- |
| Business group (supporting service change proposals) convened | 5th | DoC |
| Finalisation of allocations by DoH | 15th | DoF |
| Template contract for non acute services from DoH | 15th | DoC |
| Provider Arm Draft Business plan | 15th | PS COO |
| PBC Governance group decisions on investment proposals | 21st | DPP&CS |
| Draft Budgets | 31st | DoF |
| PBC draft business plans | 31st | DPC |
| SLA/Contract/agreement Proposals to providers | 31st | DoC |
| Final activity figures | 31st | Doc |

# February

| What | When | Lead |
| --- | --- | --- |
| Month 8 rebase predictions | 10th | DoF/DoC |
| Heads of Agreement-Service providers | 28th | DoC |
| Consortia Agreements-between commissioning bodies | 28th | DoC |
| Implementation plans-PBC Change proposals (timing subject to legal restrictions on procurement etc) | 28th | DPC |
| Negotiating teams (including PBC Leads) Finalised | 28th | DoC/DPC |
| PCT finalisation of Objectives | 28th | DPP&CS |
| PCT Performance management framework | 28th | DoC |

# March/April

| What | When | Lead |
| --- | --- | --- |
| Final budgets | 15th M | DoF |
| SLA signed | 31st M | DoC |
| Final Business Plans PCT | 31st M | DoS |
| Final Business plan Provider | 10th A | PS COO |
| Final Business Plans PBC Groups | 10th A | DPC |
| Performance objectives allocated to Directors | 10th A | CE |
| Directorate Objectives & Plans | 21st A | Directors |
| Submit LDP | 7th A | DPP&CS |

DoF=Director of Finance; DoC=Director of Commissioning (DDoC Deputy); DPC=Director of Primary Care and Service Redesign; DPP&CS=Director of Patient Public Involvement and Corporate Services

DoS=Director of Strategy; DPH=Director of Public Health; PS COO=Provider Services Chief operating Officer

Enclosure 2-Factors influencing Activity

Enclosure 3: Service Change proposals-approval process

# Text boxes

The Board is asked to:

- Note the commissioning process timetable and the business calendar it is derived from.

- Receive a report in January 2008 on the commissioning progress

Diabetic Retinopathy

Reduce acute activity from predicted out turn by elimination or alternative provision

Coding changes

Conversion ratio

18 weeks

un Bundling

PBC Service changes

Community Matrons

CAS/CATS

Trends

Trends

Demand management

ASR

Acute Contracts- Activity out turn 07/08