Children’s and Maternity Commissioning Operational Plan 2007- 08

| Key Objectives To achieve recurrent cost improvements To commission safe effective care for Children and Maternity To Participate effectively in the development of Children’s Trust Arrangements in Hertfordshire To work with Practice based commissioning groups to develop effective commissioning arrangements |
| --- |
| No. | Objective | Milestone | Tasks | Target date | Progress at June 14th 2007 | Director Manager Lead |
| 1 | To commission Children’s Continuing care services | Implement children’s cont care FRP Continuing care manager recruited to See continuing care operational plan and FRP | As set out in the financial recovery plan Link to continuing care operational plan | March 08 Mar 07 | Steering group in place and membership widened Manager post filled to commence Sept 07 Underspend on budget at end of M2 | Catherine Pelley Supported by Rachel Turvey from Sept 07 |
| 2 | Develop service specifications for all children’s services in the PCT in partnership with PbC groups | All services have agreed service specifications | Identify service areas Prioritise services Develop and agree specifications | Dec 07 | NHSP complete HV/SN/Safeguarding underway Benchmarking of HV service shows ENPCT 84/140 WPCT 108/140 further analysis of child health mapping will commence when data released at end of June | Catherine Pelley Deirdre Ginnity Julie Juliff |
| 3 | Agree maternity specification with WHHT and ENHT In line with national guidance and the West Herts review | Antenatal and postnatal pathways agreed | Specification to be issued to Trusts Performance targets agreed Pathways to be agreed and implemented PCT represented on both MSLC PCT represented on teenage pregnancy strategy group | Mar 07 Oct 07 Ongoing | Spec agreed Data from E&N Data being chased from WHHT Antenatal pathway in draft format PCT on both MSLC and teenage pregnancy group | Catherine Pelley Julie Juliff |
| 4 | To develop a rapid response to child death service | Agreed response to recommendations in Working Together | Set up task group Map current arrangements Agree gaps in provision Make recommendations to steering group | Mar 07 April 07 July 07 Sept 07 | Task group in place Mapping finished Roles and responsibilities in draft | Catherine Pelley |
| 5 | To participate in the delivery of HCT arrangements | PCT represented on both county and district partnership groups | Map current groups and PCT reps Identify all reps needed Attend meeting Establish feedback to rest of PCT | April 07 May 07 Ongoing May 07 | PCT reps agreed Ongoing work Feedback through children’s leads group established | Catherine Pelley Deirdre Ginnity Julie Juliff |
| 6 | To implement the transfer of NHSP and community children’s services from ENHT to PCT | All NHSP and community paeds services part of PCT provider services | Map services to transfer Agree implementation group needed to facilitate transfer Agree action plan to transfer Transfer completed | April 07 April 07 June 07 Mar 08 | Notice given to ENHT | Catherine Pelley Deirdre Ginnity Julie Juliff |
| 9 | To develop a strategy for children with complex health needs | Agreed multi-agency strategy in place with implementation plan | Steering group established Action plan agreed | Mar07 | Steering group has met | Catherine Pelley Deirdre Ginnity |
| 10 | To define the model for Urgent care for children in Hertfordshire as part of the ASR | Model of care for Urgent Care agreed across the county | Service redesign group to discuss UCC Establish working group to define and agree model of care Feedback into ASR process | Mar 07 April 07 July 07 | Draft UCC fro children paper in place to be incorporated into wider PCT work on UCC and OOH | Catherine Pelley Julie Juliff |
| 11 | To consult on the viability of a Birthing Unit at HH as part of ASR | Full assessment of the clinical and financial viability of the provision of HBU | Include detail of work in ASR Discuss with MSLC Set up process to assess viability Make recommendations to ASR | Mar 07 15/03/07 April 07 July 07 | Process for consultation as part of same timetable for ASR | Catherine Pelley Julie Juliff |
| 12 | To continue work on children’s service redesign expanding work across the county | Service models in place based on top 10 referrals to paediatrics | Expand redesign group across county Identify top 10 referrals Agree priorities Agree work plan for redesign Make recommendation for redesign Commission services based on new pathways of care | April 07 April 07 May 07 May 07 Oct 07 Mar 08 | WHHT to identify top 10 referrals Service redesign group to consider at July meeting 18 week analysis of all children services to be undertaken | Catherine Pelley Deirdre Ginnity Julie Juliff Debbie Felts from Sept 07 |
| 13 | To commission effective neonatal service | Agreed development plan for neonatal network | Continue network meetings Feed into SHA network review Develop plan Agree plan at network board | Ongoing | Board meets every 2 months Plan for 06/07 in place SHA review finished work ongoing to implement | Catherine Pelley |
| 14 | To continue the development of a children’s bereavement service | Bereavement service in place Plan agreed for future funding of service post NOF | Ongoing commitment to NOF service Work with Macmillan to roll out funding from 2008 | Ongoing July 07 | Service in place | Catherine Pelley |
| 15 | To work with CSF on the development of transition services for children with complex health needs | Agreed transition arrangements for children with complex health needs | Meet CSF to begin planning work Link with adult continuing care | Mar 07 |  | Catherine Pelley Deirdre Ginnity |
| 16 | To develop local commissioning arrangements for services that set out benchmarks, local tariffs and activity baselines | Agreed benchmarks for local services Agreed local tariffs Agreed activity schedules for PCT provider services | Establish meetings with PCT business team Agree work plan to develop commissioning arrangements | Mar 07 | SLA agreed with provider arm Agreed framework for working with the provider services in place | Catherine Pelley Deirdre Ginnity Julie Juliff |